DEI Projects Weekly Status Report

| Week ending: | Thursday 9th August 2012 |  |
| --- | --- | --- |
| Headlines: | - DEI002: closed 3/8 - DEI004: test file sent to EUSA for upload to MSL company 7/8 - DEI006: Phase 2 build: no progress, issues with MyEd - DEI007: feedback from Service Management and meeting with SACS - DEI008: Last Social Hub released on Monday 6/8. Requested closure |  |
| Main activities completed this week: | - DEI002 (VLE Moodle): closure approved by WIS - DEI004 (ODL in the student Record phase 2): IS created the csv test file from the new EUSA View. Being tested by MSL company. - DEI006 (Card Services): N/A - DEI008: closure requested WIS 10/8 |  |
| Planned activities not completed this week: | ACTIVITY | IMPACT & ACTION |
|  | - DEI004: sign off EUSA file (ASOR) - DEI006: phase 2 build not done, developer trying to resolve issues with ‘old’ MyEd (working ok on ‘new’ MyEd though) - DEI007: milestone sign off BRD set for 17/8 will not be met, as further meetings are required to refine scope, and to QA required student data (to be done with SACS and users) . | - DEI004: Delay live deployment to 13/8. Closure still planned for 17/8. - DEI006: Phase 2: MyEd port let and Image application – Estimate to be increased, PM to review issues with developer on Monday 13/8. - DEI007: delay of BRD sign off will not impact on the High Level Architecture Doc, as not starting before beg Oct. |
| Activities scheduled for next week: | - DEI004: To deploy EUSA View to live - DEI006: build Image Application (phase 2) - DEI007: Progress with BRD Note: all DEI projects now have the priority set to 1 within IS Apps, except DEI007: priority 2 |  |
| Major issues (include all with status=”open” and any which have changed status) (Issue status can be: open, closed or on hold) Date Raised; Target Resolution Date; Actual Resolution Date; Status; Description; Resolution; Owner; Severity (L,M, H). |
| Any other points of note: Further projects information are available on the projects webiste - DEI001 : http://www.projects.ed.ac.uk/areas/learn/dei/DEI001/index.shtml - DEI002 : http://www.projects.ed.ac.uk/areas/learn/dei/DEI002/index.shtml - DEI004 : http://www.projects.ed.ac.uk/areas/learn/dei/DEI004/index.shtml - DEI005 : http://www.projects.ed.ac.uk/areas/learn/dei/DEI005/index.shtml - DEI006 : http://www.projects.ed.ac.uk/areas/learn/dei/DEI006/index.shtml - DEI007 : http://www.projects.ed.ac.uk/areas/learn/dei/DEI007/index.shtml - DEI008 : http://www.projects.ed.ac.uk/areas/learn/dei/DEI008/index.shtml Holidays coming : Bryan MacGregor 2/7 to 13/7 Sarah Gormley 3/7 to 13/7 Franck Bergeret 13/7 to 31/7 Donna Cruickshank 16/7 to 20/7, 6/8 to 10/8 Dave Berry 20/7 to 3/8 Maurice Franceschi : 27/7 to 30/7 |  |  |