Stage: Planning

Project Terms of Reference

(ToR)

FIN082:  HMRC Real Time Information

Combined

Tax Year End & Real Time Information

Project

Finance General

AP12-003

Document Version: 1.2

Date: 01/08/12

Contents

1	Document Management	3

1.1	Contributors	3

1.2	Version Control	3

2	PROJECT OVERVIEW	4

2.1	Executive Summary	4

2.2	Business Objectives and Project Deliverables	4

2.3	Scope	5

2.4	Milestones	6

2.4.1	FIN082:	6

2.4.2	Follow-on Tax Year End & Real Time Information Project:	6

2.5	Category	7

3	PROJECT IMPACT	8

3.1	Cost Benefit Analysis	8

3.1.1	Five Year Costs	8

3.1.2	Procurement Costs and Approach	8

3.1.3	Funding	8

3.1.4	Five Year Benefits	9

3.2	Impact	9

3.3	Dependencies	9

3.4	Risks	10

4	PROJECT ORGANISATION	13

4.1	Roles and Stakeholders	13

4.2	Methodology Compliance	13

4.3	Resources	14

4.3.1	Project Resource Estimates	14

4.3.2	Post Project Resource Estimates	14

4.3.3	Dedicated Project Team?	14

4.4	Project Plans	15

4.5	Communications	15

4.6	Out of Hours Working	15

4.7	Additional Information	15

5	TOR APPROVAL	16

5.1	Approval Checklist	16

5.2	Approval Record	17

# Document Management

## Contributors

| Role | Organisation | Name |
| --- | --- | --- |
| Project Manager (Owner) | ISA Project Services | Jill Nicoll |
| Project Sponsor | Finance | Liz Welch |
| Business Project Manager | Finance FIS/Payroll | Pamela Blair |
| Business Area Manager | Finance Payroll | Kathy Chappell |
| Business Area Manager | HR | Susan McLaren |
| Business Analyst | ISA Project Services | Sue Woodger |
| Senior Analyst/Developer | ISA Config Team | Alyson Shaw |
| Support Analyst | ISA Applications Support | Ana Heyn |
| Development Technology team manager | ISA Dev Tech | Iain Fiddes |
| Technical Architect | ISA Dev Tech | Mark Lang |

## Version Control

| Date | Version | Author | Section | Amendment |
| --- | --- | --- | --- | --- |
| 20/07/12 | 1.0 | Jill N | All | Initial draft |
| 30/07/12 | 1.1 | Jill N | All | Updates resulting from ToR review meeting |
| 01/08/12 | 1.2 | Jill N | All | Updates resulting from feedback on version 1.1: Alyson S: - items previously listed under intangible costs (section 3.1.1) now moved to explain project category (section 2.5) Pamela B: - noted possible change to HMRC deadline for RTI (section 2.1) - all references to system changed to “Oracle R12” |

# PROJECT OVERVIEW

## Executive Summary

HMRC have changed the PAYE reporting regulations:

Currently, Finance sends an annual Tax Year End return to HMRC each April, for the Tax Year just ended.

From Tax Year 2013-14, employers are required to provide this information in real time, in conjunction with their regular employee pay runs.  This Real Time information (RTI) will be a fundamental change for all employers in the UK.  The new system for reporting employee pay, tax and National Insurance details will be the biggest change to the operation of PAYE since it was introduced in 1944.  Rather than submit summary details at the end of the tax year, employers will be required to communicate them to HM Revenue & Customs (HMRC) every time a payment is made to the employee.

HMRC has identified up to 106 potential pieces of information to be transmitted under the RTI programme.  36 of these are new items.  In addition, the data must be specifically linked through a code (called a “hash”) to the BACS payment made to the employee.

In April 2013, two separate deliverables will therefore be required, in order to meet HMRC regulations:

- The annual Tax Year End return, for tax year 2012-13.

- The changes required to support the new real-time returns, for tax year 2013-14 onwards.  (HMRC have indicated that the deadline for this deliverable may be delayed until later in 2013.)

This project will confirm the Terms of Reference for the scope outlined below.  A follow-on 2012-13 project, under the HR-Payroll programme, will then take the agreed requirements forward to the technical and delivery stages.

## Business Objectives and Project Deliverables

This Terms of Reference covers three separate project Proposals:

AP12-003 (FIN) – PAYE Real Time Information
AP23-005 (HRS) – HR Tax Year End 12/13
AP23-007 (HRS) – Real Time Tax Year End / Real Time Information

(AP23-007 appears to be an updated version of AP12-003)

The objectives below will be delivered not by this project, but rather by the follow-on project in planning year 2012-13.

| No | Description | New or Changed (Y/N) |
| --- | --- | --- |
| O1 | Proposal AP23-005 Successfully complete the Tax Year End process for the 2012-13 tax year: | N |
| D1 | Clone the Oracle R12 Live database and application into Oracle R12Dev and Test | Y |
| D2 | Upgrade the Oracle R12 database with Oracle’s Security Patches | N |
| D3 | Upgrade the Oracle R12application with Oracle’s latest Family Pack | N |
| D4 | Upgrade the Oracle R12application with Oracle’s latest Legislative Patches | N |
| D5 | Apply any application or output form changes required for the submission of the Tax Year End return (e.g. P60 form changes) | N |
| D6 | Timely submission of Tax Year End return for 2012-13 to HMRC | N |
| D7 | Apply any Oracle patches arising from the UK Budget of March 2013 | N |
| O2 | Proposal AP23-007 Apply all patches and updates to the Oracle application to meet RTI requirements: | N |
| D1 | Upgrade Oracle R12 database | N |
| D2 | Upgrade Oracle R12 application | N |
| D3 | Start-up of RTI submissions for 2012-13 to HMRC | N |

Reasons for changes:

Objective 1, Deliverable 1:  Clones were provided under Support for the previous Tax Year End project.  However, they will be included in this year’s project.  The IS Applications Technical Architect and Support Analyst have recommended that clones be completed before any patches are applied to Dev or Test.

Proposal AP23-007 also had a deliverable to upgrade the University’s HMRC file transfer process.  However, this deliverable has been removed from project scope.  It will be managed independently by Finance.  If any IS support is needed for this upgrade, then it will be resourced from the 2012-13 Finance Support budget.

All patches will be provided by Oracle, under the terms of the University’s existing service agreement.

The Oracle patches are available only for the R12 version of the software.  No patching work should start until after the Dev and Test environments have been cloned from Oracle R12 Live.  This project is therefore dependent upon the successful and timely delivery of the Oracle R12 upgrade project.

## Scope

The Scope of the current project is:

- To provide an approved Terms of Reference that will feed into the 2012-13 follow-on project

The Scope of the 2012-13 follow-on project is:

- Clone Oracle R12 Live to Dev and Test

- Apply any Oracle security patches.

- Apply the annual Family Pack of Oracle patches.

- Apply all Oracle patches required to support the 2012-13 annual Tax Year End submission to HMRC.

- Apply any Oracle patches arising from the UK Budget of March 2013.

- Apply all Oracle patches required to support the 2013-14 Real Time Information submissions to HMRC.

The following are outwith the scope of the projects:

- Any in-house configuration changes to the Payroll system, beyond those required for Objective 2, Deliverable 5.

- Any involvement in upgrading of the method of securely transmitting files to and from HMRC.

## Milestones

### FIN082:

| Milestone | Description | Date | Type (& Reason if Required) |
| --- | --- | --- | --- |
| Planning | when the project Terms of Reference and associated documents will be signed off | 01/08/12 | Soft |

### Follow-on Tax Year End & Real Time Information Project:

| Milestone | Description | Date | Type (& Reason if Required) |
| --- | --- | --- | --- |
| PPDR | when the design of the proposed solution will be signed off | n/a | No changes are expected to the existing Oracle R12 TAD. |
| R12 project deploys to Live | When the Oracle R12 Upgrade project deploys to HR Live. | 06/11/12 | Hard Prerequisite for start of work on Tax Year End / Real Time Information project. |
| Clone HR from Live to Dev | When the Oracle R12 Live deployment will be cloned to Dev. | 16/11/12 | Hard. Prerequisite for Dev patching. |
| Clone HR from Live to Test | When the Oracle R12 Live deployment will be cloned to Test. | 29/11/12 | Hard. Prerequisite for Test patching. |
| PPBR 1 – Security Patches PPBR 2 – Family Pack PPBR 3 – TYE patches PPBR 4 – RTI patches PPBR 5 – Budget changes | when the patches will be signed off in Dev | 20/11/12 17/12/12 11/02/13 11/02/13 end of April | Soft Depends on Oracle R12 upgrade completion, and when Oracle release the various sets of patches |
| PPIR 1 – Security Patches PPIR 2 – Family Pack PPIR 3 – TYE patches PPIR 4 – RTI patches PPIR 5 – Budget changes | when the patches will be fully integration tested and signed off by the technical team | 03/12/12 14/01/13 25/02/13 25/02/13 mid-May | Soft Depends on Oracle R12 upgrade completion, and when Oracle release the various sets of patches |
| ASoR 1 – Security Patches ASoR 2 – Family Pack ASoR 3 – TYE patches ASoR 4 – RTI patches ASoR 5 – Budget changes | when the patches will be fully acceptance tested and signed off by the customer and user community | 10/12/12 25/01/13 11/03/13 11/03/13 early June | Soft Depends on Oracle R12 upgrade completion, and when Oracle release the various sets of patches |
| Deploy 1 – Security Patches Deploy 2 – Family Pack Deploy 3 – TYE patches Deploy 4 – RTI patches Deploy 5 – Budget changes | when the patches will be deployed in the live environment | 18/01/13 15/02/13 05/04/13 05/04/13 mid-June | Hard * Legislative requirements |
| DSoR 1 – Security Patches DSoR 2 – Family Pack DSoR 3 – TYE patches DSoR 4 – RTI patches DSoR 5 – Budget changes | when the patches will be signed off following successful deployment | 01/02/13 01/03/13 19/04/13 19/04/13 early July | Soft |
| Closure | when all closure activities will be completed | late July | Soft |

* The actual deployment dates will be confirmed with the Payroll Business Manager when the 2013 Payroll timetables become available.

## Category

Planning year 2011-12 project FIN082 is an Essential External project.

The planning year 2012-13 follow-on project will be an Essential External project.

Reasons for the above category are:

- The reputation of the University would be severely adversely impacted if the legislative requirements of this project were not met by 6th April 2013.

- Oracle 11.5 will become unsupported by Oracle from April 2013.  That is, the Payroll system would be unsupported by its provider if the legislative requirements of this project were not met by 6th April 2013.

- The Payroll cannot be run in Oracle R12 until all legislative patches for Tax Year End have been applied.  Therefore, salary payments to staff could not be made from April 2013 if the legislative requirements of this project were not met by 6th April 2013.

# PROJECT IMPACT

## Cost Benefit Analysis

### Five Year Costs

- Proposal Estimates:

| - Tangible Costs Summary (£ 275 pd): |  |  |  |  |
| --- | --- | --- | --- | --- |
| - 5 Year - Summary | - IT Services i.e. IS staff, hardware, software and services | - Support Group Staff Costs | - College Staff Costs | - Total |
| - Costs - PAYE | - £ 20,625 | £ 11,000 | £ 0 | £ 31,625 |
| - Costs - TYE | - £ 34,375 | £ 17,325 | £ 0 | £ 51,700 |
| - Costs - RTI | - £ 32,450 | £ 17,325 | £ 0 | £ 49,775 |
| - Costs - Total | - £ 87,450 | £ 45,650 | £ 0 | £ 133,100 |

- ToR Estimates:

| - Tangible Costs Summary (£ 275 pd): |  |  |  |  |
| --- | --- | --- | --- | --- |
| - 5 Year - Summary | - IT Services i.e. IS staff, hardware, software and services | - Support Group Staff Costs | - College Staff Costs | - Total |
| - Costs - FIN082 | £ 4,950 | £ 1,375 | £ 0 | £ 6,325 |
| - Costs - 12-13 project | £ 40,700 | £ 13,750 | £ 0 | £ 54,450 |
| - Costs - Total | £ 45,650 | £ 15,125 | £ 0 | £ 60,775 |

| - Intangible Costs |  |
| --- | --- |
| - Cost | - Assumptions |

### Procurement Costs and Approach

| - Procurement Costs - 4 Year Summary |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | - Hardware | - Software | - Services | - Total |
| - Costs | £ 0 | £ 0 | £ 0 | £ 0 |
| - Assumptions | - It is assumed that all required database and application patches will be provided within the scope of the University’s existing Oracle service contract. No costs are therefore anticipated for the TYE/RTI project. |  |  |  |

### Funding

Planning year 2011-12 project FIN082 will be funded from the Finance programme budget.

The planning year 2012-13 follow-on project will be funded from the HR-Finance programme budget.

Funding for the resourcing of these projects has been secured through the Annual Planning process.

### Five Year Benefits

| - Tangible Benefits Summary |  |  |  |  |
| --- | --- | --- | --- | --- |
| - 5 Year - Summary | - IT Services | - Support Groups | - Colleges (including Students) | - Total |
| - Benefits | - n/a | n/a | n/a | n/a |

- n/a:  No staff cost savings are anticipated.

- These are Essential External projects, required in order to satisfy legislative requirements.

| - Tangible Benefits |  |  |
| --- | --- | --- |
| - Description | - Saving | - Total |
| n/a |  |  |

| - Intangible Benefits |  |
| --- | --- |
| - Benefit | - Assumptions |
| n/a |  |

- Updated Project Cost Benefit Workbook (secure)

## Impact

| - Service or Project | - Description of Impact or Dependency | - Project/Service Manager Aware (Y/N) |
| --- | --- | --- |
| n/a | This project is not expected to impact any other projects, or on any other ISA service. |  |

## Dependencies

This project may be impacted by the following projects and services:

| - Service or Project | - Description of Impact or Dependency | - Project/ Service Manager Aware (Y/N) |
| --- | --- | --- |
| HR R12 Upgrade | This project is dependent upon the successful and timely delivery of the Oracle R12 upgrade: - The Oracle patches that this project seeks to apply are available only for the R12 version of Oracle. - This project strongly recommends that the Live Oracle R12 system be cloned into Dev before patching commences in Dev. This is to ensure consistency between the Dev and Live systems to which the patches are being applied. As a worst case scenario, if the Oracle R12 deployment to Live is delayed beyond 6th November, then patching may have to start in Dev without the clone from Live. The Project Sponsor has accepted the risk of this scenario. - This project has a prerequisite that the Live Oracle R12 system be cloned into Test. This is to ensure consistency between the Test and Live systems to which the patches are being applied. It is also to provide UAT testers with meaningful test data. The risk of applying patches to a Test system that is inconsistent with the Live environment is too great a risk for the project to accept. Patching will not commence in Test until the Clone from Live has been completed. - The current target date for Oracle R12 deployment to Live is 6th November 2012. This leaves only 5 months (minus 2 weeks for Christmas closure) for all of this project’s patching phases to be completed. This is very tight, and is a project risk. | Y |
| Salary Award processing | This project requires that key Payroll resources are available to perform UAT testing during the tight timescale between the Oracle patches becoming available and the delivery milestones. However, it is believed that at least some of these timeslots may coincide with the critical period during which the Payroll staff are required to process the University’s annual salary award. | Y |
| Auto Enrolment | As above, for Payroll resources. | Y |
| eRecruitment | The project’s Config team resource is heavily committed to this project. | Y |

## Risks

| - No - Date Raised | - Description | - Impact / Probability | - Risk Management Approach |
| --- | --- | --- | --- |
| 1 04/07/12 | Plan to run both the TYE and the RTI proposals as a single project. Resulting risk of confusion between the two proposals in the parallel delivery. | Medium / Low | Retain. Reduces risk of clashes between two separate projects. Allows closer control, by same PM. |
| 2 04/07/12 | Two different sets of requirements are both required for the same delivery date. Resulting risk of incompatibility between the two sets of requirements. | Medium / Medium | Retain. The legislative requirement is to deliver both together. |
| 3 04/07/12 | Risk that Oracle R12 upgrade delayed. Resulting risk of delay to start of HMRC patching. | High / Medium – Oracle R12 is not a priority zero project. | Reduce. Request high priority for Oracle R12 upgrade project, due to impact on this (EE) legislative project. |
| 4 04/07/12 | Risk that ISA resource not available when needed by project plan. Resulting risk of project slippage. Ultimate risk of failing to meet legislative deadlines | High / Low – Historically, resourcing has not been an issue. | Reduce. Request high priority for HMRC project. |
| 5 04/07/12 | Risk that Payroll resource not available when needed by project plan. Resulting risk of project slippage. Ultimate risk of failing to meet legislative deadlines. | High / Low – Historically, resourcing has not been an issue. | Retain. |
| 6 04/07/12 | Risk that Oracle patches not available when needed by project plan. Resulting risk of not enough time to UAT test. | High / Low – Historically, delivery times have been satisfactory. | Share with Oracle |
| 7 04/07/12 | Risk that HMRC continue to change requirements, beyond the date by which changes can be applied and tested, and the milestones still met. Resulting risk of not enough time to UAT test, and /or of not meeting milestones. | High / High | Share with HMRC |
| 8 04/07/12 | Difficulty of fitting the Live deployment dates into the busy Payroll Live business processing timetables. Resulting risk of not being able to meet milestones. | Medium / Low | Retain. |
| 9 04/07/12 | Change-over from Apps Mgt to Config team for application patching. Current understanding: - Ana to assess Oracle documentation and plan application patching; Alyson to shadow. - Alyson to perform patching; Ana to mentor/advise. Risk of confusing responsibilities. | Medium / Low | Retain. |
| 10 30/07/12 | Risk that Finance may require IS support for its independent activity of upgrading its file transfer process. (This activity has been removed from project scope.) | Low / Low | Transfer to Project Sponsor’s Support budget. |

Link to Project Risk Register

# PROJECT ORGANISATION

## Roles and Stakeholders

| Role | Who | Responsibilities |
| --- | --- | --- |
| Project Manager | Jill Nicoll |  |
| Programme Manager | Rhian Davies |  |
| Project Sponsor | Liz Welch Terry Fox | Finance sponsorship Finance (Payroll & Pensions) sponsorship |
| Business Area Manager | Pamela Blair |  |
| Payroll Manager | Kathy Chappell | Specifies dates on which Live deployments may be applied. Arranges for data entry of any new fields required by project. |
| HR System Owner | Susan McLaren |  |
| Legislative body | HMRC | Specifies legislative requirements |
| Provider | Oracle | Provides HR system patches to meet the legislative requirements. |

Additional information on Roles and Stakeholder information is also provided in the Project Roles, Project Stakeholder Map and Stakeholder Communication Plan.

## Methodology Compliance

| Methodology Stage | Standard Stage Sign-Off | Project Approach |
| --- | --- | --- |
| Planning | Approval by Project Manager, Project Sponsors and IS Applications Management Team (WIS) | Standard. ToR review meeting with stakeholders. Business Area Manager may be authorised to represent Project Sponsors. |
| Business Analysis | Peer Project Analysis Review (PPAR) | N/A – no business analysis required |
| System Analysis & Design | Peer Project Design Review (PPDR) | N/A – no system analysis or design required. No changes expected to Oracle R12 TAD. |
| Build | Peer Project Build Review (PPBR) | Patches applied by Dev Tech and Config. Tested in Dev by Config. Sign-off by email. |
| Integration | Peer Project Integration Review (PPIR) | Patches applied by Dev Tech and Config. Tested in Test by Apps Mgt and Config. Sign-off by email. |
| Acceptance | Acceptance Sign-Off Review (ASOR) | Standard. UAT review meetings, to confirm sign-off to deploy to Live. |
| Deployment | Deployment Sign-Off Review (DSOR) | Sign-off by email. |
| Closure | Closure Review and Approval by Project Manager, Project Sponsors and IS Applications Management Team | Closure questionnaire distributed for feedback. Closure document based on responses. Sign-off by email. Business Area Manager may be authorised to represent Project Sponsors. |

## Resources

### Project Resource Estimates

| Original Estimate | Revised Estimate | Reason for Revision |
| --- | --- | --- |
| IS Applications Staff Resource |  |  |
| PAYE - 75 TYE – 125 RTI - 118 | FIN082 - 18 Follow-on Project - 148 | The ToR’s terms are different to those of the three proposals. |
| Support Group Staff Resource |  |  |
| PAYE - 40 TYE - 63 RTI - 63 | FIN082 - 10 Follow-on Project 1 - 50 | The ToR’s terms are different to those of the three proposals. |
| College Staff and Student Resource |  |  |
| 0 | 0 |  |
| Hardware Software and Service Costs |  |  |
| £ 0 | £ 0 |  |

Updated IS Applications Staff Resource Estimate.

### Post Project Resource Estimates

| Original Estimate | Revised Estimate | Reason for Revision |
| --- | --- | --- |
| IS Applications Staff Resource |  |  |
| 0 | 0 |  |
| Support Group Staff Resource |  |  |
| 0 | 0 |  |
| College Staff and Student Resource |  |  |
| 0 | 0 |  |
| Hardware Software and Service Costs |  |  |
| 0 | 0 |  |

Payroll and Tax Year End are already covered by existing support arrangements.

### Dedicated Project Team?

Does the Project Manager recommend that the project be assigned a dedicated Project Team?   NO

## Project Plans

Updated Project Plan – for FIN082 project only.

## Communications

| Who | What | When | By Whom |
| --- | --- | --- | --- |
| Project Sponsors | Programme Report | Monthly | Programme Managers |
| Programme Managers | Programme Reports One-to-One | Monthly | Project Manager(s) |
| Payroll director | Progress updates | Ad hoc | Business area managers |
| Pensions manager | Progress updates | Ad hoc | Business area managers |
| Business Area managers | Project meetings, to be scheduled according to the needs of the project | Regularly, as needed | Project Manager(s) and ISA project team |

Updated Stakeholder Communications Plan.

## Out of Hours Working

Under prior arrangements, if a live deployment is expected to require more than 2 days of system downtime, then consideration will be given to out of hours working.

It is not currently known how long the various sets of Oracle patches will take to load.  Estimates will be provided following the deployment to Development.  Each batch of patching is not expected to take more than 2 days.  However, the down-time for all patching will be scheduled to start on a Wednesday evening, to allow for a contingency overrun into the weekend.

Evening working will be required.  Weekend working may be required.  TOIL will be provided.

No other out of hours working is anticipated at this time.

## Additional Information

HMRC information (website)

Live deployments must be scheduled to avoid conflict with the Payroll timetables.  These are:

- October 2012

- November 2012

- December 2012

Payroll timetables are not yet available for 2013.

# TOR APPROVAL

## Approval Checklist

| Check List Item (ToR Reference) | Quality Criteria | Complete Y/N | Reviewed By |
| --- | --- | --- | --- |
| Category and Billing Arrangements | - Category correctly assigned - Billing arrangements agreed with all parties | Y Y | Jill N |
| Scope, Objectives and Deliverables (2.2, 2.3) | - Boundaries for project clearly identified. - Objectives and deliverables clearly identified. | Y Y | Jill N |
| Milestones (2.4) | - All milestones identified | Y | Jill N |
| Costs (3.1.1) | - Five year costs identified including any recurrent costs | Y | Jill N |
| Procurement Approach (3.1.2) | - Procurement approach identified and in line with established best practice | Y | Jill N |
| Funding | - Sources of funding identified - Funding secured - Any special payment terms identified | Y Y Y | Jill N |
| Benefits (3.1.4) | - Five year benefits identified and realistic. - Realisation approach stated | n/a | Jill N |
| Project and Service Impacts (3.3) | - Impacts identified - Project/Service management aware | n/a | Jill N |
| Risk (3.4) | - Risk Register complete - Highest Impact/Probability risks identified - Clear and sensible Risk Management Approach | Y Y Y | Jill N |
| Roles and Stakeholders (4.1) | - Project Roles identified - Evidence of appropriate Project Sponsor commitment - Evidence of IS awareness and commitment - Evidence of customer engagement | Y Y Y Y | Jill N |
| Resource Estimate (4.3.1) | - Credible estimate completed with appropriate engagement of all parties - Assumptions clearly stated - Required actions taken where estimate exceeds original project proposal estimate | Y Y n/a | Jill N |
| Project Plan (4.4) | - Project plan exists and is credible - Evidence that plan will be used to drive the project | Y (project 1) Y | Jill N |

## Approval Record

| TOR Raised By | Jill Nicoll |
| --- | --- |
| Date Raised | 20/07/12 |
| Date TOR Reviewed | 30/07/12 |
| Date TOR Approved | 01/08/12 |