## Order of Events
| Archibus and Database Upgrade - Order of events | Dept. | Who | Start | Expected completion | Comment
| Remove V17 package from the App store | Desktops | Mark W/Myles Ewan | Friday Night (30/11) | Friday Evening | This will remove V17 from peoples machines.
| Bring down database | Dev Tech | Mark L | Saturday 8:00 pm | Saturday 8:00 pm
Take cold back-up |  | Dev Tech | Mark L | Saturday 8:00 pm | Saturday 8:00 pm | Defined roll back point
| Upgrade to 11g as per instructions | Dev Tech | Mark L | Saturday 8:00 pm | Saturday overnight | Needs to be available for MASS upgrade the next day.
| Check 11g upgrade completed successfully | Dev Tech | Mark L | Sunday 8:00 | Monday 8:00 | All OK , carry on. Otherwise take copy of upgraded LIVE database for investigation and go through rollback procedure.
| Roll Out Trigger change for Monthly billing | App Management | Ron Macleod | Monday 09:00 | Monday 09:00 | Can happen anytime post 11g upgrade
| Build three W7 Smart client PCS for Drawing Office - Myles | Desktops | Myles Ewan | Monday 09:00 | Monday 12:00
| Upgrade EBIS Office XP machine with Archibus 19 manually - Myles | Desktops | Myles Ewan | Monday 09:00 | Monday 12:00
| In reception, upgrade the Monthly Billing PC. To be upgraded to W7 | Desktops | Myles Ewan | Monday 09:00 | Monday 12:00 | Required before Tuesday Test
| Upgrade Database to Archibus 19 | MASS/ Dev Tech | Martin Matt/ Riky | Monday 10:15 | Monday 14:00 | MASS to upgrade as per install procedure already carried out in DEV and TEST
| Configure WebCentral Archibus to 19.3 | MASS/ Dev Tech | Martin Matt/ Riky | Monday 10:15 | Monday 14:00 | MASS to upgrade as per install procedure already carried out in DEV and TEST
| Configure/Update EBIS Web Components for Live Database | MASS/ Dev Tech | Martin Matt/ Riky | Monday 10:15 | Monday 14:00 | MASS to upgrade as per install procedure already carried out in DEV and TEST
Upgrade / Set-up smartclient/AutoCAD | Configure Archibus/AutoCAD overlay PCs | MASS | Martin Matt | Monday 10:15 | Monday 14:00
| Run DB comparison on TEST and LIVE to ensure match. | Tech Man | David Foggo | Monday 14:00 | Monday 14:00 | Any discrepancies can be reconciled and remediated by MASS representative.
| E&B Testers , run functionality checks | E&B | E&B group testers | Monday 15:00 | Monday / Tuesday | Run through normal production work cycles such as invoicing on LIVE
| Checkpoint to review status | All | All | Monday 16:00 | Monday 16:00 | Review status of upgrade and testing and decide to progress. All OK , carry on. Otherwise take copy of upgraded LIVE database for investigation and go through rollback procedure.
| E&B Testers , run functionality checks | E&B | E&B group testers | Tuesday | Tuesday | Run through normal production work cycles such as invoicing on LIVE
| Carry out specific Tests and cover issues which arose previously in Testing to ensure changes carried through to LIVE | EBIS Office | Jane Cooney | Tuesday 9:00 | Tuesday | Run through pre-determined tests and JIRA scenarios to ensure all code versions applied correctly.
| Checkpoint to review status | All | All | Tuesday 2:00 (or Earlier) |  | Review any issues or problems that may have arisen and determine if service levels acceptable. If not , discuss options including Rollback.
| All remaining E&B users to publish v19 from the App store | Select Estates Users | All | Tuesday/Wednesday | Tuesday | E&B users to follow previously issued instructions to publish v19 to their workstations
| Normal Ongoing operation | EBIS users | All | From Tuesday/ Wednesday | From Wednesday | E&B users to follow previously issued instructions to publish v19 to their workstations
| Sign Off on Upgrade | All | All | Wednesday
Official DSOR | Official DSOR | All |  | Monday+2 weeks |  | Or after all Monthly/Weekly processing has completed. TBD
| Identify any outlying PCs which may need upgraded | EBIS |  | Ongoing
Rollback On the event of an error
| Take EBIS off-line | Dev Tech | Mark L | n/a
| Remove v19 from the AppStore | Desk tops | Mark W |  | circa 1/2 hour | These steps to regress have been tested before the go-live date.
Republish v17 package |  | Desk tops | Mark W |  | circa 1/2 hour | These steps to regress have been tested before the go-live date.
| revert to 10g | Dev Tech | Mark L |  | 1 hour
| Bring EBIS Live back up | Dev Tech | Mark L |  | 5 mins
| Restart Archibus | Dev Tech | Riky |  | 5 mins
| User Check | EBIS | Pauline |  | 1 hour