## SItes
KEY |  |  | cPanel
Plesk
AWS
Scheduled for closure
IS Apps Hosting
Transition out of LTS portfolio (owner to take responsibility)
Service Name | Date | Owner | Migration status (Migrated / In Progress / Ready / Not migrated / Not To Be Migrated | OS | DB | Target WebServer | Target DB Server | SSL | IP | Alias | Assignee
clinicaleducation.mvm.ed.ac.uk |  | DLAM AD (IS LTW) | Migrated | Linux | MySQL | cPanel | cPanel | Valid until 12/03/2016 | 129.215.10.97
demo.essq.ed.ac.uk |  | DLAM AD (IS LTW) | Migrated | Linux | n/a | cPanel | cPanel |  | 129.215.10.97
gpst.mvm.ed.ac.uk |  | DLAM AD (IS LTW) | Migrated | Linux | MySQL | cPanel | cPanel | Valid until 03/09/2016 | 129.215.10.97 |  | Matt Hammond
gracescore.co.uk |  | WGI IC (IS LTW) | Migrated | Linux | MySQL | cPanel | cPanel |  | 129.215.10.97 |  | Matt Hammond
heartelearning.org |  | WGI IC (IS LTW) | Migrated | Linux | MySQL | cPanel | cPanel |  | 129.215.10.97 |  | Matt Hammond
pdc-demo.dentistry.ed.ac.uk |  | DLAM AD (IS LTW) | Migrated | Linux | n/a | cPanel | cPanel |  | 129.215.10.97 |  | Matt Hammond
sefce.net |  | DLAM AD (IS LTW) | Migrated | Linux | MySQL | cPanel | cPanel | Valid until 08/08/2016 | 129.215.10.97 |  | Matt Hammond
test.climate.ed.ac.uk |  | WGI IC (IS LTW) | Migrated | Windows | MySQL | winweb2t.is.ed.ac.uk | sql-db-winwebt |  | 129.215.234.113 | winweb2t-vwww1.is.ed.ac.uk | Matt Hammond
test.escript.law.ed.ac.uk |  | DLAM AD (IS LTW) | Migrated | Windows | MSSQL | winweb2t.is.ed.ac.uk | sql-db-winwebt |  | 129.215.234.114 | winweb2t-vwww2.is.ed.ac.uk | Matt Hammond
test.labyrinth.mvm.ed.ac.uk |  | DLAM AD (IS LTW) | Migrated | Windows | MSSQL | winweb2t.is.ed.ac.uk | sql-db-winwebt |  | 129.215.234.115 | winweb2t-vwww3.is.ed.ac.uk
test.learning.essq.ed.ac.uk |  | DLAM AD (IS LTW) | Migrated | Windows | MySQL | winweb2t.is.ed.ac.uk | sql-db-winwebt |  | 129.215.234.116 | winweb2t-vwww4.is.ed.ac.uk
test.learning.gensurg.ed.ac.uk |  | DLAM AD (IS LTW) | Migrated | Windows | MySQL | winweb2t.is.ed.ac.uk | sql-db-winwebt |  | 129.215.234.117 | winweb2t-vwww5.is.ed.ac.uk
test.learning.orthosurg.ed.ac.uk |  | DLAM AD (IS LTW) | Migrated | Windows | MySQL | winweb2t.is.ed.ac.uk | sql-db-winwebt |  | 129.215.234.118 | winweb2t-vwww6.is.ed.ac.uk
test.learning.urosurg.ed.ac.uk |  | DLAM AD (IS LTW) | Migrated | Windows | MySQL | winweb2t.is.ed.ac.uk | sql-db-winwebt |  | 129.215.234.119 | winweb2t-vwww7.is.ed.ac.uk
test.learning.vascular.ed.ac.uk |  | DLAM AD (IS LTW) | Migrated | Windows | MySQL | winweb2t.is.ed.ac.uk | sql-db-winwebt |  | 129.215.234.120 | winweb2t-vwww8.is.ed.ac.uk
test.ooer.labyrinth.mvm.ed.ac.uk |  | DLAM AD (IS LTW) | Migrated | Windows | MSSQL | winweb2t.is.ed.ac.uk | sql-db-winwebt |  | 129.215.234.121 | winweb2t-vwww9.is.ed.ac.uk
test.tutorialbooking.com |  | DLAM AD (IS LTW) | Migrated | Windows | MySQL | winweb2t.is.ed.ac.uk | sql-db-winwebt |  | 129.215.234.121 | winweb2t-vwww9.is.ed.ac.uk | Matt Hammond
test.learning.ophthalmology.ed.ac.uk |  | DLAM AD (IS LTW) | Migrated | Windows | MySQL | winweb2t.is.ed.ac.uk | sql-db-winwebt |  | 129.215.234.122 | winweb2t-vwww10.is.ed.ac.uk | Matt Hammond
test.pdc.dentistry.ed.ac.uk |  | DLAM AD (IS LTW) | Migrated | Windows | MySQL | winweb2t.is.ed.ac.uk | sql-db-winwebt |  | 129.215.234.123 | winweb2t-vwww11.is.ed.ac.uk
test.learning.surgery.ed.ac.uk |  | DLAM AD (IS LTW) | Migrated | Windows | MySQL | winweb2t.is.ed.ac.uk | sql-db-winwebt |  | 129.215.234.124 | winweb2t-vwww12.is.ed.ac.uk
climate.ed.ac.uk |  | WGI IC (IS LTW) | Migrated | Windows | MySQL | winweb2.is.ed.ac.uk | sql-db-winweb2.is.ed.ac.uk |  | 129.215.234.125 | winweb2-vwww1.is.ed.ac.uk
escript.law.ed.ac.uk | 2015-10-30 | DLAM AD (IS LTW) | Migrated | Windows | MSSQL | winweb2.is.ed.ac.uk | sql-db-winweb2.is.ed.ac.uk | 2015-05-23 | 129.215.234.126 | winweb2-vwww2.is.ed.ac.uk | Matt Hammond
labyrinth.mvm.ed.ac.uk | 2015-09-09 | DLAM AD (IS LTW) | Migrated | Windows | MSSQL | winweb2.is.ed.ac.uk | sql-db-winweb2.is.ed.ac.uk | 2018-04-13 | 129.215.234.127 | winweb2-vwww3.is.ed.ac.uk | Matt Hammond
learning.essq.ed.ac.uk | 2015-09-09 | DLAM AD (IS LTW) | Migrated | Windows | MySQL | winweb2.is.ed.ac.uk | sql-db-winweb2.is.ed.ac.uk | 2018-04-22 | 129.215.234.128 | winweb2-vwww4.is.ed.ac.uk
learning.gensurg.ed.ac.uk | 2015-09-09 | DLAM AD (IS LTW) | Migrated | Windows | MySQL | winweb2.is.ed.ac.uk | sql-db-winweb2.is.ed.ac.uk |  | 129.215.234.129 | winweb2-vwww5.is.ed.ac.uk
learning.orthosurg.ed.ac.uk | 2015-09-09 | DLAM AD (IS LTW) | Migrated | Windows | MySQL | winweb2.is.ed.ac.uk | sql-db-winweb2.is.ed.ac.uk |  | 129.215.234.130 | winweb2-vwww6.is.ed.ac.uk | Matt Hammond
learning.urosurg.ed.ac.uk | 2015-09-09 | DLAM AD (IS LTW) | Migrated | Windows | MySQL | winweb2.is.ed.ac.uk | sql-db-winweb2.is.ed.ac.uk |  | 129.215.234.131 | winweb2-vwww7.is.ed.ac.uk | Matt Hammond
learning.vascular.ed.ac.uk | 2015-09-09 | DLAM AD (IS LTW) | Migrated | Windows | MySQL | winweb2.is.ed.ac.uk | sql-db-winweb2.is.ed.ac.uk |  | 129.215.234.132 | winweb2-vwww8.is.ed.ac.uk
ooer.labyrinth.mvm.ed.ac.uk | 2015-09-09 | DLAM AD (IS LTW) | Migrated | Windows | MSSQL | winweb2.is.ed.ac.uk | sql-db-winweb2.is.ed.ac.uk |  | 129.215.234.133 | winweb2-vwww9.is.ed.ac.uk
opthalmology.mvm.ed.ac.uk | 2015-09-09 | DLAM AD (IS LTW) | Migrated | Windows | MySQL | winweb2.is.ed.ac.uk | sql-db-winweb2.is.ed.ac.uk | 2018-04-22 | 129.215.234.134 | winweb2-vwww10.is.ed.ac.uk
pdc.dentistry.ed.ac.uk | 15/8/2015 | DLAM AD (IS LTW) | Migrated | Windows | MySQL | winweb2.is.ed.ac.uk | sql-db-winweb2.is.ed.ac.uk | 2015-10-11 | 129.215.234.135 | winweb2-vwww11.is.ed.ac.uk
tutorialbooking.com |  | DLAM AD (IS LTW) | Migrated | Windows | MSSQL | winweb2.is.ed.ac.uk | sql-db-winweb2.is.ed.ac.uk | Valid until 20/09/2015 | 129.215.234.136 | winweb2-vwww12.is.ed.ac.uk
test.com-mand.info |  | DLAM AD (IS LTW) | Migrated | Windows | MySQL | collmed-test.is.ed.ac.uk | sql-db-collmedt |  | 129.215.234.137 | collmed-test-vwww1.is.ed.ac.uk | Matt Hammond
test.eevec.vet.ed.ac.uk |  | DLAM AD (IS LTW) | Migrated | Windows | MSSQL | collmed-test.is.ed.ac.uk | sql-db-collmedt |  | 129.215.234.138 | collmed-test-vwww2.is.ed.ac.uk | Pat Fleury
test.exam.mvm.ed.ac.uk |  | DLAM AD (IS LTW) | Migrated | Windows | MSSQL | cmvmex-test.is.ed.ac.uk | sql-db-cmvmexamt |  | 129.215.234.139 | cmvmex-test-vwww1.is.ed.ac.uk | Matt Hammond
test.eros.mvm.ed.ac.uk |  | DLAM AD (IS LTW) | Migrated | Windows | MSSQL | collmed-test.is.ed.ac.uk | sql-db-collmedt |  | 129.215.234.139 | collmed-test-vwww3.is.ed.ac.uk | Matt Hammond
test.oscaplus.net |  | DLAM AD (IS LTW) | Migrated | Windows | MySQL | cmvmex-test.is.ed.ac.uk | sql-db-cmvmexamt |  | 129.215.234.140 | cmvmex-test-vwww2.is.ed.ac.uk | Matt Hammond
test.pathcal.ac.uk |  | DLAM AD (IS LTW) | Migrated | Windows | MSSQL | collmed-test.is.ed.ac.uk | sql-db-collmedt |  | 129.215.234.140 | collmed-test-vwww4.is.ed.ac.uk
com-mand.info |  | DLAM AD (IS LTW) | Migrated | Windows | MySQL | collmed.is.ed.ac.uk | sql-db-collmed.is.ed.ac.uk | 2016-06-24 | 129.215.234.143 | collmed-vwww1.is.ed.ac.uk | Matt Hammond
eevec.vet.ed.ac.uk | 2015-11-19 | DLAM AD (IS LTW) | Migrated | Windows | MSSQL | collmed.is.ed.ac.uk | sql-db-collmed.is.ed.ac.uk | 2017-05-13 | 129.215.234.144 | collmed-vwww2.is.ed.ac.uk
eros.mvm.ed.ac.uk | 2015-11-17 | DLAM AD (IS LTW) | Migrated | Windows | MSSQL | collmed.is.ed.ac.uk | sql-db-collmed.is.ed.ac.uk | 2016-04-18 | 129.215.234.145 | collmed-vwww3.is.ed.ac.uk | Matt Hammond
pathcal.ac.uk | 2015-11-17 | DLAM AD (IS LTW) | Migrated | Windows | MSSQL | collmed.is.ed.ac.uk | sql-db-collmed.is.ed.ac.uk | 2017-03-04 | 129.215.234.146 | collmed-vwww4.is.ed.ac.uk | Matt Hammond
exam.mvm.ed.ac.uk | 2015-11-17 | DLAM AD (IS LTW) | Migrated | Windows | MSSQL | cmvmex.is.ed.ac.uk | sql-db-cmvmexam.is.ed.ac.uk | 2017-11-24 | 129.215.234.151 | cmvmex-vwww1.is.ed.ac.uk | Matt Hammond
oscaplus.net | 2015-09-09 | DLAM AD (IS LTW) | Migrated | Windows | MySQL | cmvmex.is.ed.ac.uk | sql-db-cmvmexam.is.ed.ac.uk | 2016-03-11 | 129.215.234.152 | cmvmex-vwww2.is.ed.ac.uk | Matt Hammond
test.eemec.med.ed.ac.uk |  | DLAM AD (IS LTW) | Migrated | Windows | MSSQL/MySQL | eemec-test.is.ed.ac.uk | sql-db-eemect |  | 129.215.234.153 | eemec-test-vwww1.is.ed.ac.uk | Matt Hammond
eemec.med.ed.ac.uk | 2015-11-17 | DLAM AD (IS LTW) | Migrated | Windows | MSSQL/MySQL | eemec.is.ed.ac.uk | sql-db-eemec.is.ed.ac.uk | 2016-11-04 | 129.215.234.154 | eemec-vwww1.is.ed.ac.uk | Matt Hammond
learning.surgery.ed.ac.uk |  | DLAM AD (IS LTW) | Migrated | Windows | MySQL | winweb2.is.ed.ac.uk | sql-db-winweb2.is.ed.ac.uk |  | 129.215.234.155 | winweb2-vwww13.is.ed.ac.uk | Matt Hammond
portfolio.mvm.ed.ac.uk | 2015-11-17 | DLAM AD (IS LTW) | Migrated | Windows | MSSQL | eemec.is.ed.ac.uk | sql-db-eemec.is.ed.ac.uk | 2017-04-23 | 129.215.234.179 | eemec-vwww2.is.ed.ac.uk | Matt Hammond
test.portfolio.mvm.ed.ac.uk |  | DLAM AD (IS LTW) | Migrated | Windows | MSSQL | eemec-test.is.ed.ac.uk | sql-db-eemect |  | 129.215.234.179 | eemect-vwww2.is.ed.ac.uk | Matt Hammond
pft.mvm.ed.ac.uk | 27/01/2016 | DLAM AD (IS LTW) | Migrated | Windows | MSSQL | winweb2.is.ed.ac.uk | sql-db-winweb |  | 129.215.234.189 | winweb2-vwww14.is.ed.ac.uk | Matt Hammond
clinicalaudit.mvm.ed.ac.uk | 27/01/2016 | WGI IC (IS LTW) | Migrated | Windows | MSSQL | winweb2.is.ed.ac.uk | sql-db-winweb |  | 129.215.234.190 | winweb2-vwww15.is.ed.ac.uk | Matt Hammond
www.diabetesframe.org | 27/01/2016 | WGI IC (IS LTW) | Migrated | Windows | MSSQL | winweb2.is.ed.ac.uk | sql-db-winweb |  | 129.215.234.191 | winweb2-vwww16.is.ed.ac.uk
infectioncontrol.mvm.ed.ac.uk | 27/01/2016 | WGI IC (IS LTW) | Migrated | Windows | MSSQL | winweb2.is.ed.ac.uk | sql-db-winweb |  | 129.215.234.192 | winweb2-vwww17.is.ed.ac.uk
recal.mvm.ed.ac.uk | 27/01/2016 | WGI IC (IS LTW) | Migrated | Windows | MSSQL | winweb2.is.ed.ac.uk | sql-db-winweb |  | 129.215.234.193 | winweb2-vwww18.is.ed.ac.uk
strokeadvancingmodules.org | 27/01/2016 | WGI IC (IS LTW) | Migrated | Windows | MSSQL | winweb2.is.ed.ac.uk | sql-db-winweb |  | 129.215.234.194 | winweb2-vwww19.is.ed.ac.uk
strokecorecompetencies.org | 27/01/2016 | WGI IC (IS LTW) | Migrated | Windows | MSSQL | winweb2.is.ed.ac.uk | sql-db-winweb |  | 129.215.234.195 | winweb2-vwww20.is.ed.ac.uk
stroketraining.org | 27/01/2016 | WGI IC (IS LTW) | Migrated | Windows | MSSQL | winweb2.is.ed.ac.uk | sql-db-winweb |  | 129.215.234.196 | winweb2-vwww21.is.ed.ac.uk | Matt Hammond
virtualpharmacologylab.com | 27/01/2016 | WGI IC (IS LTW) | Migrated | Windows | MSSQL | winweb2.is.ed.ac.uk | sql-db-winweb |  | 129.215.234.207 | winweb2-vwww22.is.ed.ac.uk
clinicaleducation-old.mvm.ed.ac.uk | 27/01/2016 | DLAM AD (IS LTW) | Migrated | Windows | MSSQL | winweb2.is.ed.ac.uk | sql-db-winweb |  | 129.215.234.208 | winweb2-vwww23.is.ed.ac.uk
archive.learning.essq.ed.ac.uk | 27/01/2016 | DLAM AD (IS LTW) | Migrated | Windows | MSSQL | winweb2.is.ed.ac.uk | sql-db-winweb |  | 129.215.234.209 | winweb2-vwww24.is.ed.ac.uk
www.iconzafrica.org | 28/01/2016 | WGI IC (IS LTW) | Migrated | Windows | MSSQL | winweb2.is.ed.ac.uk | sql-db-winweb |  | 129.215.234.210 | winweb2-vwww25.is.ed.ac.uk
test.medine2.com | 2016-02-12 | WGI IC (IS LTW) | Migrated | Windows | MSSQL | winweb2.is.ed.ac.uk | sql-db-winweb |  | 129.215.234.211 | winweb2t-vwww21.is.ed.ac.uk
learning-analysis.info |  | DLAM AD (IS LTW) | Not to be Migrated | Linux |  | AWS | AWS | Valid until 07/12/2015
psapilot.net |  | DLAM AD (IS LTW) | Not to be Migrated | Linux |  | AWS | AWS
breastcancer.mvm.ed.ac.uk |  | WGI IC (IS LTW) | Not to be Migrated | Windows | MSSQL | Plesk | Plesk
carmms.mvm.ed.ac.uk |  | WGI IC (IS LTW) | Not to be Migrated | Windows | MSSQL | Plesk | Plesk
chronic-migraine.co.uk |  | WGI IC (IS LTW) | Not to be Migrated | Windows | MSSQL | Plesk | Plesk |  |  |  | Pat Fleury
ewriting.org.uk ¦ ewriting.org.uk |  | EDE (IS LTW) | Not to be Migrated | Windows | MSSQL | Plesk | Plesk |  |  |  | Pat Fleury
hme.mvm.ed.ac.uk |  | DLAM AD (IS LTW) | Not to be Migrated | Windows | MSSQL | Plesk | Plesk
lodopp.net |  | WGI IC (IS LTW) | Not to be Migrated | Windows | MSSQL | Plesk | Plesk |  |  |  | Pat Fleury
lts-archive.mvm.ed.ac.uk |  | WGI IC (IS LTW) | Not to be Migrated | Windows | MSSQL | Plesk | Plesk |  |  |  | Pat Fleury
malawi.mvm.ed.ac.uk |  | EDE (IS LTW) | Not to be Migrated | Windows | MSSQL | Plesk | Plesk |  |  |  | Pat Fleury
medine2.com | 2106-02-12 | WGI IC (IS LTW) | Migrated | Windows | MSSQL | winweb2.is.ed.ac.uk | sql-db-winweb |  |  |  | Matt Hammond
medine2.info ¦ medine2.info ¦ medine2.org ¦ medine2.org ¦ medine2.com |  | WGI IC (IS LTW) | Not to be Migrated | Windows | MSSQL | Plesk | Plesk
socletrial.org |  | WGI IC (IS LTW) | Migrated | Linux | MySQL | cPanel | cPanel
tuning-medicine.com |  | WGI IC (IS LTW) | Not to be Migrated | Windows | MSSQL | Plesk | Plesk
archive.euanmacdonaldcentre.com |  | WGI IC (IS LTW) | Not To Be Migrated | [7 empty] | Matt Hammond
bmto.ed.ac.uk |  | LTS | Not To Be Migrated | n/a | [6 empty] | Matt Hammond
bookings.mvm.ed.ac.uk |  | LTS | ? | n/a |  |  |  | Valid until 21/05/2015 |  |  | Matt Hammond
cdll.mvm.ed.ac.uk |  | LTS | Not To Be Migrated | n/a | [6 empty] | Matt Hammond
dentistry.mvm.ed.ac.uk |  | DLAM AD (IS LTW) | Not To Be Migrated | [7 empty] | Matt Hammond
eemed.mvm.ed.ac.uk |  | LTS | Not To Be Migrated
eepop.mvm.ed.ac.uk |  | LTS | Not To Be Migrated
egrad.mvm.ed.ac.uk |  | LTS | Not To Be Migrated | [7 empty] | Matt Hammond
emsec.mvm.ed.ac.uk |  | LTS | Not To Be Migrated
oralhealth.mvm.ed.ac.uk |  | LTS | Not To Be Migrated | n/a | [6 empty] | Matt Hammond
orthotherapy.mvm.ed.ac.uk |  | LTS | Not To Be Migrated | n/a
scottishdoctor.org |  | LTS | Not To Be Migrated | n/a | [6 empty] | Matt Hammond
www.clive.ed.ac.uk |  | LTS | Not To Be Migrated | n/a | [6 empty] | Matt Hammond
test.com-mand.info |  | DLAM AD (IS LTW) | Migrated | Windows | MySQL | collmed-test.is.ed.ac.uk | sql-db-collmedt.is.ed.ac.uk |  |  |  | Matt Hammond

## DB migrations
Current SRV | Current DB Name | New DB Server | New DB Name | Complete
srv6ltsmvm.mvm.ed.ac.uk | cal | sql-db-cmvmexamt.is.ed.ac.uk | cal
srv6ltsmvm.mvm.ed.ac.uk | casm | sql-db-collmedt.is.ed.ac.uk | casm
srv6ltsmvm.mvm.ed.ac.uk | eevec | sql-db-collmedt.is.ed.ac.uk | eevec
srv6ltsmvm.mvm.ed.ac.uk | eemec | sql-db-eemect.is.ed.ac.uk | eemec
srv6ltsmvm.mvm.ed.ac.uk | escript | sql-db-winwebt.is.ed.ac.uk | escript
srv15ltsmvm.mvm.ed.ac.uk | labyrinth | sql-db-winwebt.is.ed.ac.uk | labyrinth
srv6ltsmvm.mvm.ed.ac.uk | ooer_labyrinth | sql-db-winwebt.is.ed.ac.uk | ooer_labyrinth
srv6ltsmvm.mvm.ed.ac.uk | ele | sql-db-winwebt.is.ed.ac.uk | ele
srv6ltsmvm.mvm.ed.ac.uk | portfolio | sql-db-winwebt.is.ed.ac.uk | portfolio
srv6ltsmvm.mvm.ed.ac.uk | casm | sql-db-collmed.is.ed.ac.uk | casm
srv6ltsmvm.mvm.ed.ac.uk | cal | sql-db-cmvmexam.is.ed.ac.uk | cal
srv6ltsmvm.mvm.ed.ac.uk | eevec | sql-db-collmed.is.ed.ac.uk | eevec
srv6ltsmvm.mvm.ed.ac.uk | eemec | sql-db-eemec.is.ed.ac.uk | eemec
srv6ltsmvm.mvm.ed.ac.uk | escript | sql-db-winweb.is.ed.ac.uk | escript
srv15ltsmvm.mvm.ed.ac.uk | labyrinth | sql-db-winweb.is.ed.ac.uk | labyrinth
srv15ltsmvm.mvm.ed.ac.uk | ooer_labyrinth | sql-db-winweb.is.ed.ac.uk | ooer_labyrinth
srv6ltsmvm.mvm.ed.ac.uk | ele | sql-db-winweb.is.ed.ac.uk | ele
srv8ltsmvm.mvm.ed.ac.uk | portfolio | sql-db-winweb.is.ed.ac.uk | portfolio
srv15ltsmvm.mvm.ed.ac.uk | eemec2001 | sql-db-eemect.is.ed.ac.uk | eemec2001
srv15ltsmvm.mvm.ed.ac.uk | eemec2002 | sql-db-eemect.is.ed.ac.uk | eemec2002
srv15ltsmvm.mvm.ed.ac.uk | eemec2003 | sql-db-eemect.is.ed.ac.uk | eemec2003
srv15ltsmvm.mvm.ed.ac.uk | eemec2004 | sql-db-eemect.is.ed.ac.uk | eemec2004
srv15ltsmvm.mvm.ed.ac.uk | eemec2005 | sql-db-eemect.is.ed.ac.uk | eemec2005
srv15ltsmvm.mvm.ed.ac.uk | eemec2006 | sql-db-eemect.is.ed.ac.uk | eemec2006
srv15ltsmvm.mvm.ed.ac.uk | eemec2007 | sql-db-eemect.is.ed.ac.uk | eemec2007
srv15ltsmvm.mvm.ed.ac.uk | eemec2008 | sql-db-eemect.is.ed.ac.uk | eemec2008
srv15ltsmvm.mvm.ed.ac.uk | eemec2009 | sql-db-eemect.is.ed.ac.uk | eemec2009
srv15ltsmvm.mvm.ed.ac.uk | eemec2010 | sql-db-eemect.is.ed.ac.uk | eemec2010
srv15ltsmvm.mvm.ed.ac.uk | eemec2011 | sql-db-eemect.is.ed.ac.uk | eemec2011
srv15ltsmvm.mvm.ed.ac.uk | eemec2012 | sql-db-eemect.is.ed.ac.uk | eemec2012
srv6ltsmvm.mvm.ed.ac.uk | eemec2013 | sql-db-eemect.is.ed.ac.uk | eemec2013
srv6ltsmvm.mvm.ed.ac.uk | eemec2014 | sql-db-eemect.is.ed.ac.uk | eemec2014
srv15ltsmvm.mvm.ed.ac.uk | eevec2003 | sql-db-collmedt.is.ed.ac.uk | eevec2003
srv15ltsmvm.mvm.ed.ac.uk | eevec2004 | sql-db-collmedt.is.ed.ac.uk | eevec2004
srv15ltsmvm.mvm.ed.ac.uk | eevec2005 | sql-db-collmedt.is.ed.ac.uk | eevec2005
srv15ltsmvm.mvm.ed.ac.uk | eevec2006 | sql-db-collmedt.is.ed.ac.uk | eevec2006
srv15ltsmvm.mvm.ed.ac.uk | eevec2007 | sql-db-collmedt.is.ed.ac.uk | eevec2007
srv15ltsmvm.mvm.ed.ac.uk | eevec2008 | sql-db-collmedt.is.ed.ac.uk | eevec2008
srv15ltsmvm.mvm.ed.ac.uk | eevec2009 | sql-db-collmedt.is.ed.ac.uk | eevec2009
srv15ltsmvm.mvm.ed.ac.uk | eevec2010 | sql-db-collmedt.is.ed.ac.uk | eevec2010
srv15ltsmvm.mvm.ed.ac.uk | eevec2011 | sql-db-collmedt.is.ed.ac.uk | eevec2011
srv15ltsmvm.mvm.ed.ac.uk | eevec2012 | sql-db-collmedt.is.ed.ac.uk | eevec2012
srv6ltsmvm.mvm.ed.ac.uk | eevec2013 | sql-db-collmedt.is.ed.ac.uk | eevec2013
srv6ltsmvm.mvm.ed.ac.uk | eevec2014 | sql-db-collmedt.is.ed.ac.uk | eevec2014
srv15ltsmvm.mvm.ed.ac.uk | eemec2001 | sql-db-eemec.is.ed.ac.uk | eemec2001
srv15ltsmvm.mvm.ed.ac.uk | eemec2002 | sql-db-eemec.is.ed.ac.uk | eemec2002
srv15ltsmvm.mvm.ed.ac.uk | eemec2003 | sql-db-eemec.is.ed.ac.uk | eemec2003
srv15ltsmvm.mvm.ed.ac.uk | eemec2004 | sql-db-eemec.is.ed.ac.uk | eemec2004
srv15ltsmvm.mvm.ed.ac.uk | eemec2005 | sql-db-eemec.is.ed.ac.uk | eemec2005
srv15ltsmvm.mvm.ed.ac.uk | eemec2006 | sql-db-eemec.is.ed.ac.uk | eemec2006
srv15ltsmvm.mvm.ed.ac.uk | eemec2007 | sql-db-eemec.is.ed.ac.uk | eemec2007
srv15ltsmvm.mvm.ed.ac.uk | eemec2008 | sql-db-eemec.is.ed.ac.uk | eemec2008
srv15ltsmvm.mvm.ed.ac.uk | eemec2009 | sql-db-eemec.is.ed.ac.uk | eemec2009
srv15ltsmvm.mvm.ed.ac.uk | eemec2010 | sql-db-eemec.is.ed.ac.uk | eemec2010
srv15ltsmvm.mvm.ed.ac.uk | eemec2011 | sql-db-eemec.is.ed.ac.uk | eemec2011
srv15ltsmvm.mvm.ed.ac.uk | eemec2012 | sql-db-eemec.is.ed.ac.uk | eemec2012
srv15ltsmvm.mvm.ed.ac.uk | eemec2013 | sql-db-eemec.is.ed.ac.uk | eemec2013
srv6ltsmvm.mvm.ed.ac.uk | eemec2013 | sql-db-eemec.is.ed.ac.uk | eemec2013
srv6ltsmvm.mvm.ed.ac.uk | eemec2014 | sql-db-eemec.is.ed.ac.uk | eemec2014
srv15ltsmvm.mvm.ed.ac.uk | eevec2003 | sql-db-collmed.is.ed.ac.uk | eevec2003
srv15ltsmvm.mvm.ed.ac.uk | eevec2004 | sql-db-collmed.is.ed.ac.uk | eevec2004
srv15ltsmvm.mvm.ed.ac.uk | eevec2005 | sql-db-collmed.is.ed.ac.uk | eevec2005
srv15ltsmvm.mvm.ed.ac.uk | eevec2006 | sql-db-collmed.is.ed.ac.uk | eevec2006
srv15ltsmvm.mvm.ed.ac.uk | eevec2007 | sql-db-collmed.is.ed.ac.uk | eevec2007
srv15ltsmvm.mvm.ed.ac.uk | eevec2008 | sql-db-collmed.is.ed.ac.uk | eevec2008
srv15ltsmvm.mvm.ed.ac.uk | eevec2009 | sql-db-collmed.is.ed.ac.uk | eevec2009
srv15ltsmvm.mvm.ed.ac.uk | eevec2010 | sql-db-collmed.is.ed.ac.uk | eevec2010
srv15ltsmvm.mvm.ed.ac.uk | eevec2011 | sql-db-collmed.is.ed.ac.uk | eevec2011
srv15ltsmvm.mvm.ed.ac.uk | eevec2012 | sql-db-collmed.is.ed.ac.uk | eevec2012
srv6ltsmvm.mvm.ed.ac.uk | eevec2013 | sql-db-collmed.is.ed.ac.uk | eevec2013
srv6ltsmvm.mvm.ed.ac.uk | eevec2014 | sql-db-collmed.is.ed.ac.uk | eevec2014

## SSL
Domain Name | Use | Expiry Date | Type | Scope | Server(s) | Load-balanced | Email address | TAD
exam.mvm.ed.ac.uk | front |  | GS | Live | MSSQL | No
oscaplus.net | both |  | GS | Live | MySQL | No
com-mand.info | both |  | GS | Live | MySQL | No
eevec.vet.ed.ac.uk | both |  | GS | Live | MSSQL | No
eros.mvm.ed.ac.uk | front |  | GS | Live | MSSQL | No
pathcal.ac.uk | front |  | GS | Live | MSSQL | No
pft.mvm.ed.ac.uk | front |  | GS | Live | MSSQL | No
eemec.med.ed.ac.uk | both |  | GS | Live | MSSQL/MySQL | No
climate.ed.ac.uk | both |  | GS | Live | MySQL | No
escript.law.ed.ac.uk | both |  | GS | Live | MSSQL | No
labyrinth.mvm.ed.ac.uk | front |  | GS | Live | MSSQL | No
learning.essq.ed.ac.uk | both |  | GS | Live | MySQL | No
learning.gensurg.ed.ac.uk | both |  | GS | Live | MySQL | No
learning.orthosurg.ed.ac.uk | both |  | GS | Live | MySQL | No
learning.urosurg.ed.ac.uk | both |  | GS | Live | MySQL | No
learning.vascular.ed.ac.uk | both |  | GS | Live | MySQL | No
ooer.labyrinth.mvm.ed.ac.uk | front |  | GS | Live | MSSQL | No
opthalmology.mvm.ed.ac.uk | both |  | GS | Live | MySQL | No
pdc.dentistry.ed.ac.uk | both |  | GS | Live | MySQL | No
portfolio.mvm.ed.ac.uk | front |  | GS | Live | MSSQL | No
learning.surgery.ed.ac.uk | both |  | GS | Live | MySQL | No
test.exam.mvm.ed.ac.uk | front |  | GS | Test | MSSQL | No
test.oscaplus.net | both |  | GS | Test | MySQL | No
test.com-mand.info | both |  | GS | Test | MySQL | No
test.eevec.vet.ed.ac.uk | both |  | GS | Test | MSSQL | No
test.eros.mvm.ed.ac.uk | front |  | GS | Test | MSSQL | No
test.pathcal.ac.uk | front |  | GS | Test | MSSQL | No
test.pft.mvm.ed.ac.uk | front |  | GS | Test | #N/A | No
test.eemec.med.ed.ac.uk | both |  | GS | Test | MSSQL/MySQL | No
test.climate.ed.ac.uk | both |  | GS | Test | MySQL | No
test.escript.law.ed.ac.uk | both |  | GS | Test | MSSQL | No
test.labyrinth.mvm.ed.ac.uk | front |  | GS | Test | MSSQL | No
test.learning.essq.ed.ac.uk | both |  | GS | Test | MySQL | No
test.learning.gensurg.ed.ac.uk | both |  | GS | Test | MySQL | No
test.learning.orthosurg.ed.ac.uk | both |  | GS | Test | MySQL | No
test.learning.urosurg.ed.ac.uk | both |  | GS | Test | MySQL | No
test.learning.vascular.ed.ac.uk | both |  | GS | Test | MySQL | No
test.ooer.labyrinth.mvm.ed.ac.uk | both |  | GS | Test | MSSQL | No
test.learning.ophthalmology.ed.ac.uk | both |  | GS | Test | MySQL | No
test.pdc.dentistry.ed.ac.uk | both |  | GS | Test | MySQL | No
test.portfolio.mvm.ed.ac.uk | front |  | GS | Test | MSSQL | No
test.learning.surgery.ed.ac.uk | both |  | GS | Test | MySQL | No