## - old plan
Project: | EST080 |  |  |  |  | Project Manager: |  |  |  | Anne Mathison | [5 empty] | Business Lead: |  |  |  | Colin Pritchard
2015-10-15
Task | Start Date | Due Date | IS days | Lead | Involves liaison with | % Complete | time axis 2015-08-10 to 2016-06-27
1. System Demonstration |  |  |  | CP | bar: 2015-09-07 to 2015-09-28; 2015-11-02 to 2015-11-30; 2016-01-04 to 2016-01-25; 2016-03-07 to 2016-03-28; 2016-05-02 to 2016-05-30
Current system
1.1 Project Team | 2015-07-29 | 2015-08-21 |  | CP | Stevie, Brian | 100 | bar: 2015-08-10 to 2015-08-17
1.2 Estates Management | 2015-08-03 | 2015-08-03 |  | CP | GT, GB | 100 | bar: 2015-08-10
2. System Familiarisation - Project Team representatives |  |  |  | CP / PS | bar: 2015-09-07 to 2015-09-28; 2015-11-02 to 2015-11-30; 2016-01-04 to 2016-01-25; 2016-03-07 to 2016-03-28; 2016-05-02 to 2016-05-30
2.1 1/2 day workshop | 2015-08-18 | 2015-08-18 |  | CP / PS | Project Team | 100 | bar: 2015-08-17
3. Fault Types |  |  |  | CP | bar: 2015-09-07 to 2015-09-28; 2015-11-02 to 2015-11-30; 2016-01-04 to 2016-01-25; 2016-03-07 to 2016-03-28; 2016-05-02 to 2016-05-30
3.1. Complete first draft of Fault types | 2015-08-17 | 2015-09-04 |  | CP | except heating engineers | 90 | bar: 2015-08-10 to 2015-08-31; 2015-10-12
3.2. Initial QA check by Thomson Bethune | 2015-08-17 | 2015-09-04 |  | CP |  | 90 | bar: 2015-08-10 to 2015-09-07
3.3. Define and update Test system with required fault types | 2015-08-17 | 2015-08-21 |  | CP/PS/JB | PS set up | 100 | bar: 2015-08-10 to 2015-08-24
3.4. Clarify strategy regarding inserting data into Live | 2015-08-31 | 2015-09-04 |  | PS/JB | bar: 2015-08-31
4. Outstanding Issues |  |  |  | Pauline/Anne/Martin | bar: 2015-09-07 to 2015-09-28; 2015-11-02 to 2015-11-30; 2016-01-04 to 2016-01-25; 2016-03-07 to 2016-03-28; 2016-05-02 to 2016-05-30
4.1. Determine status regarding outstand issues | 2015-08-17 | 2015-08-21 |  | JC / AS |  | 100 | bar: 2015-08-17 to 2015-08-24
4.2 Resolve outstanding issues | 2015-08-17 | 2015-09-04 |  | Project team | Mass | bar: 2015-08-17 to 2015-08-31; 2015-10-05 to 2015-10-12
5. Application Enhancements |  |  |  | Pauline,Maureen,Colin, | bar: 2015-09-07 to 2015-09-28; 2015-11-02 to 2015-11-30; 2016-01-04 to 2016-01-25; 2016-03-07 to 2016-03-28; 2016-05-02 to 2016-05-30
5.1. Define additional functional requirements | 2015-07-19 | 2015-09-04 |  | Project team | Mass | 100 | bar: 2015-08-10
5.2. Confirm specification of functional requirements | 2015-08-17 | 2015-08-21 |  | Project Team |  | 100 | bar: 2015-08-10 to 2015-08-24
5.2.2 Stock Issue specify | 2015-08-24 | 2015-09-21 |  | PS |  | 100 | bar: 2015-08-17 to 2015-08-24; 2015-09-21
5.2.4 Stock Issue Defined | 2015-08-31 | 2015-09-21 |  | PS |  | 100 | bar: 2015-08-24; 2015-09-21
5.3. Approval to raise PO for additional functional requirements | 2015-08-17 | 2015-09-22 |  | GT | MM 345956 | 100 | bar: 2015-08-17 to 2015-08-31; 2015-09-21
5.4 Development of additional functional enhancements | 2015-09-23 | 2015-10-20 |  | Mass | MM | bar: 2015-08-31 to 2015-10-19
5.5 Install additional functional changes on Dev and Test | 2015-10-16 | 2015-10-20 |  | RH | 16 + 20 Oct RH | bar: 2015-09-21; 2015-10-12 to 2015-10-19
5.6 Complete UAT of additional functional enhancements | 2015-10-19 | 2015-10-30 |  | PS / JB / CP | Mass | bar: 2015-09-28 to 2015-10-05; 2015-10-19 to 2015-10-26
7. Complete Test System Configuration |  |  |  | CP / PS / JB | bar: 2015-09-07 to 2015-09-28; 2015-11-02 to 2015-11-30; 2016-01-04 to 2016-01-25; 2016-03-07 to 2016-03-28; 2016-05-02 to 2016-05-30
7.1. Define tests to be undertaken during user acceptance testing | 2015-08-17 | 2015-08-28 |  | PS/ JB / CP | CP | bar: 2015-08-17 to 2015-08-31
7.2. Complete configuration of Test system to support User Acceptance Testing | 2015-08-24 | 2015-10-09 |  | PS / JB | CP | bar: 2015-08-24 to 2015-09-14; 2015-10-19 to 2015-10-26
1. Further System Demonstration post enhancements) |  |  |  | CP | bar: 2015-09-07 to 2015-09-28; 2015-11-02 to 2015-11-30; 2016-01-04 to 2016-01-25; 2016-03-07 to 2016-03-28; 2016-05-02 to 2016-05-30
1.4 Project Team | 2015-11-02 | 2015-11-06 |  | CP | Trades Reps | bar: 2015-11-02
1.5 Estates Management | 2015-11-09 | 2015-11-13 |  | CP | GB, DB | bar: 2015-11-09
1.6 Trades Teams Road Shows | 2015-10-05 | 2015-10-23 |  | CP/AS/MM | bar: 2015-11-09 to 2015-11-23
6. Business Users Consultation Process |  |  |  | MM / AS / CP | bar: 2015-09-07 to 2015-09-28; 2015-11-02 to 2015-11-30; 2016-01-04 to 2016-01-25; 2016-03-07 to 2016-03-28; 2016-05-02 to 2016-05-30
6.1. Devise overall strategy and associated communications | 2015-08-17 | 2015-08-28 |  | MM / AS / CP | bar: 2015-08-17 to 2015-08-24
6.2 Analyse existing fault reporting users and calls logged | 2015-08-17 | 2015-08-28 |  | JB / AS | bar: 2015-08-17 to 2015-08-24
6.3 Define and establish business contacts - DPOS | 2015-08-10 | 2015-08-28 |  | MM |  | 75 | bar: 2015-08-10 to 2015-08-24
6.4 Business Partner Roadshows | 2015-08-31 | 2015-10-30 |  | MM / CP / AS | bar: 2015-08-31 to 2015-10-26
8. User Acceptance Testing |  |  |  | Project Team | bar: 2015-09-07 to 2015-09-28; 2015-11-02 to 2015-11-30; 2016-01-04 to 2016-01-25; 2016-03-07 to 2016-03-28; 2016-05-02 to 2016-05-30
8.1. Document full test script and review | 2015-09-21 | 2015-10-30 |  | Project team | bar: 2015-09-21 to 2015-10-05; 2015-10-26
8.2. Complete UAT | 2015-11-02 | 2015-11-13 |  | Project team | bar: 2015-11-02 to 2015-11-09
9. Load Testing |  |  |  | Gordon McK | bar: 2015-09-07 to 2015-09-28; 2015-11-02 to 2015-11-30; 2016-01-04 to 2016-01-25; 2016-03-07 to 2016-03-28; 2016-05-02 to 2016-05-30
9.1. Review report from Development Technology re strategy | 2015-08-24 | 2015-08-28 |  | Gordon McK |  | 90 | bar: 2015-08-10 to 2015-08-24
9.2. Prepare load testing script | 2015-09-28 | 2015-10-09 |  | Dev Tech | bar: 2015-09-28 to 2015-10-05
9.3. Undertake load testing | 2015-11-09 | 2015-11-13 |  | Dev Tech | bar: 2015-10-26
10. Reporting | bar: 2015-09-07 to 2015-09-28; 2015-11-02 to 2015-11-30; 2016-01-04 to 2016-01-25; 2016-03-07 to 2016-03-28; 2016-05-02 to 2016-05-30
10.1 Review standard WebCentral reports | 2015-08-31 | 2015-09-11 |  | CP/ PS / JB | bar: 2015-08-31 to 2015-09-07
10.2 Determine any additional reporting | 2015-09-14 | 2015-09-25 |  | CP/ PS / JB | bar: 2015-09-14 to 2015-09-21; 2015-10-26
11. User Training |  |  |  | Pauline | bar: 2015-09-07 to 2015-09-28; 2015-11-02 to 2015-11-30; 2016-01-04 to 2016-01-25; 2016-03-07 to 2016-03-28; 2016-05-02 to 2016-05-30
11.1. Create user guide – admin | 2015-08-10 | 2015-08-28 |  | PS / JB | bar: 2015-08-10 to 2015-08-24
11.2. Create user guide – users | 2015-08-10 | 2015-10-16 |  | PS / JB | bar: 2015-08-10 to 2015-10-12
11.3. Document training stratgy | 2015-09-28 | 2015-10-09 |  | Project team | bar: 2015-09-28 to 2015-10-05
11.4. User training | 2015-11-16 | 2015-12-04 |  | Project team | bar: 2015-11-02 to 2015-11-30
12. Configure Live System |  |  |  | PS / JB | bar: 2015-09-07 to 2015-09-28; 2015-11-02 to 2015-11-30; 2016-01-04 to 2016-01-25; 2016-03-07 to 2016-03-28; 2016-05-02 to 2016-05-30
12.1 Complete configuration of Live System | 2015-11-16 | 2015-11-26 |  | PS / JB | bar: 2015-11-16 to 2015-11-23
13. Roll Out |  |  |  | CP/MM/PS | bar: 2015-09-07 to 2015-09-28; 2015-11-02 to 2015-11-30; 2016-01-04 to 2016-01-25; 2016-03-07 to 2016-03-28; 2016-05-02 to 2016-05-30
13.1. Define rollout strategy | 2015-10-05 | 2015-10-16 |  | CP /MM / PS | AM / AS | bar: 2015-10-05 to 2015-10-12
13.2. Roll-out | 2015-11-26 | 2015-12-18 |  | CP /MM / PS | AM / AS | bar: 2015-11-02 to 2015-11-30
13.3. Post roll-out support | 2015-11-09 | 2015-12-04 |  | CP /MM / PS | AM / AS | bar: 2015-11-02 to 2015-11-30
Close Project |  |  |  | Anne | bar: 2015-09-07 to 2015-09-28; 2015-11-02 to 2015-11-30; 2016-01-04 to 2016-01-25; 2016-03-07 to 2016-03-28; 2016-05-02 to 2016-05-30
Close Project | 2015-11-23 | 2015-12-11 |  | AM | Project Team | bar: 2015-11-23 to 2015-12-07
total days |  |  | 0
MILESTONE
Planned dates
Completed | Complete | bar: 2015-08-10 to 2015-08-31
Not Started/delayed

## Current Plan
Project: | EST080 |  |  |  |  | Project Manager: |  |  |  | Anne Mathison | [5 empty] | Business Lead: |  |  |  | Colin Pritchard
2016-02-04
Task | Start Date | Due Date | IS days | Lead | Involves liaison with | % Complete | 2016-01-25 | 2016-02-01 | 2016-02-08 | 2016-02-15 | 2016-02-22 | 2016-02-29 | 2016-03-07 | 2016-03-14 | 2016-03-21 | 2016-03-28 | 2016-04-04 | 2016-04-11 | 2016-04-18 | 2016-04-25 | 2016-05-02 | 2016-05-09 | 2016-05-16 | 2016-05-23 | 2016-05-30 | 2016-06-06 | 2016-06-13 | 2016-06-20 | 2016-06-27
1. System Development | bar: 2016-01-25; 2016-03-07 to 2016-03-28; 2016-05-02 to 2016-05-30
Mobile Application
Remaining fixes to be supplied | 2016-02-01 | 2016-02-09 |  | AM | Mass | bar: 2016-02-01 to 2016-02-08
Remaining fixes to be tested | 2016-02-10 | 2016-02-12 |  | PS, JB | Mass | bar: 2016-02-08
Sign off Fixes | 2016-02-15 | 2016-02-15 |  | ProjTeam
Back Office Operations | bar: 2016-01-25; 2016-03-07 to 2016-03-28; 2016-05-02 to 2016-05-30
Work Order Sequencing
Windows Client Changes | 2016-02-15 | 2016-02-26 |  | IS | Mass | bar: 2016-02-15 to 2016-02-22
EBIS on-Line changes | 2016-02-15 | 2016-02-26 | y | AS, JA | Mass | bar: 2016-02-15 to 2016-02-22
Test dual Fault reporting testing (of WebCentral and EBIS online) | 2016-02-29 | 2016-03-04 | yes | PS, JB | JA | bar: 2016-02-29
Month-End re-charging and archiving
Define Month-End Billing and Archiving Requirements | 2016-02-08 | 2016-02-12 | y | PS, JB | AS, JA | bar: 2016-02-08
Confirm functional change spec | 2016-02-15 | 2016-02-19 |  | ProjTeam | bar: 2016-02-15
Develop Month End Archiving Requirements | 2016-02-22 | 2016-03-04 | y | AS, JA | PS, JB | bar: 2016-02-22 to 2016-02-29
User testing and re-work | 2016-03-07 | 2016-03-18 |  | PS, JB | bar: 2016-03-07 to 2016-03-14
2. System Testing | bar: 2016-01-25; 2016-03-07 to 2016-03-28; 2016-05-02 to 2016-05-30
Complete Scenario testing using WebCentral on new HelpDesk | 2016-02-15 | 2016-02-26 |  | PS, JB CP | bar: 2016-02-15 to 2016-02-22
Complete PPM testing on WebCentral | 2016-02-29 | 2016-03-04 |  | PS, JB | bar: 2016-02-29
Contingency to complete all testing | 2016-03-07 | 2016-03-11 | yes | PS, JB | JA | bar: 2016-03-07
Complete parallel helpdesk testing | 2016-03-14 | 2016-03-18 |  | PS, JB | bar: 2016-03-14
Complete month-end re-charging and archiving | 2016-03-21 | 2016-03-25 |  | PS/JB | IS Apps | bar: 2016-03-21
Performance Testing dates agree dates? | 2016-02-22 | 2016-02-26 | yes | Dev Tech | bar: 2016-03-21 to 2016-03-28
Acceptance Testing Milestone | 2016-04-15 | 2016-04-15 | ?? | bar: 2016-03-28
User consultation | bar: 2016-01-25; 2016-03-07 to 2016-03-28; 2016-05-02 to 2016-05-30
Estates Trades Department - System Awareness
New System Familiarisation for Trades 1 | 2016-03-14 | 2016-03-18 |  | CP PS, JB | Trades | bar: 2016-03-14
New System Familiarisation for Trades 2 | 2016-03-21 | 2016-03-25 |  | CP PS, JB | Trades | bar: 2016-03-21
New System Familiarisation for Trades 3 | 2016-03-28 | 2016-04-01 |  | CP PS, JB | Trades | bar: 2016-03-28
Business Partners - Fault Reporters
Systems Consultation | 2016-03-14 | 2016-04-22 |  | CP, MM | bar: 2016-03-14 to 2016-04-18
Go Live Preparations | bar: 2016-01-25; 2016-03-07 to 2016-03-28; 2016-05-02 to 2016-05-30
Prepare User Guide
Prepare User guide | 2016-03-28 | 2016-04-22 |  | Proj Team | bar: 2016-03-28 to 2016-04-18
Review and complete user guide | 2016-04-25 | 2016-04-29 |  | Proj Team | bar: 2016-04-25
Live System Configuration
Complete Live System Configuration | 2016-04-04 | plan |  | PS, JB | bar: 2016-04-04 to 2016-04-25
Zone Rollout (x4)
Each Zone - Roll out Zone | stagger | [5 empty] | 2016-04-25: zone diff colours
Complete Zone related user configuration | 2016-05-02 | 2016-05-06 | bar: 2016-05-02
Complete user training - zone champions | 2016-05-09 | 2016-05-13 | bar: 2016-05-09
Complete user training | 2016-05-16 | 2016-05-20 |  | PS, JB | bar: 2016-05-16
Deploy HelpDesk Application to Tradesmen Phones | 2016-05-16 | 2016-05-20 | bar: 2016-05-16
Go-Live in Zone | 2016-05-23 | 2016-05-23 |  | PS, JB | bar: 2016-05-23
Post GoLive support | 2016-05-23 | 2016-05-27 | bar: 2016-05-23
Related Project Activities | bar: 2016-01-25; 2016-03-07 to 2016-03-28; 2016-05-02 to 2016-05-30
Mobile Phone Rollout | 2016-02-15 | 2016-02-19 | bar: 2016-02-15
Building Floor Plans
Create demo SmartClient Environment | 2016-02-15 | 2016-03-11 | bar: 2016-02-15 to 2016-03-07
Arrange Demo of SmartClient to Space Planners | 2016-03-14 | 2016-03-18 | bar: 2016-03-14
Determine strategy to create mobile friendly floor plans | 2016-03-14 | 2016-03-18 | bar: 2016-03-14
Create mobile friendly floor plans | 2016-03-20 | 2016-04-15 | bar: 2016-03-21 to 2016-04-11
EST091 EBIS On-Line Upgrade | bar: 2016-01-25; 2016-03-07 to 2016-03-28; 2016-05-02 to 2016-05-30
Complete Planning | 2016-02-01 | 2016-02-26 |  | IS Apps | bar: 2016-02-01 to 2016-02-22
Development | 2016-02-29 | 2016-03-25 |  | CL | AM | bar: 2016-02-29 to 2016-03-21
Test | 2016-03-28 | 2016-04-08 |  | PS, JB | CL, AM | bar: 2016-03-28 to 2016-04-04
Live | 2016-04-11 | 2016-04-15 |  | CL | PS, JB, AM | bar: 2016-04-11
Operational Reports | bar: 2016-01-25; 2016-03-07 to 2016-03-28; 2016-05-02 to 2016-05-30
Review WebCentral Reports | 2016-02-15 | 2016-02-26 | bar: 2016-02-15 to 2016-02-22
Confirm operational requirements | 2016-02-15 | 2016-02-19 |  | CP | bar: 2016-02-15
Task | Start Date | Due Date | IS days | Lead | Involves liaison with | % Complete | 2016-01-25 | 2016-02-01 | 2016-02-08 | 2016-02-15 | 2016-02-22 | 2016-02-29 | 2016-03-07 | 2016-03-14 | 2016-03-21 | 2016-03-28 | 2016-04-04 | 2016-04-11 | 2016-04-18 | 2016-04-25 | 2016-05-02 | 2016-05-09 | 2016-05-16 | 2016-05-23 | 2016-05-30 | 2016-06-06 | 2016-06-13 | 2016-06-20 | 2016-06-27
MILESTONE
Planned dates
Completed | Complete | bar: 2016-01-25 to 2016-02-15
Not started/delayed/planned

## temp-Tasks Plan
Project: EST080 |  | Project Manager: |  |  |  | Anne Mathison | [5 empty] | Business Lead: |  |  |  | Colin Pritchard
2016-02-16
Date | Team | Liason | 2016-02-15 | 2016-02-22 | 2016-02-29 | 2016-03-07 | 2016-03-14 | 2016-03-21 | 2016-03-28 | 2016-04-04 | 2016-04-11 | 2016-04-18 | 2016-04-25 | 2016-05-02 | 2016-05-09 | 2016-05-16 | 2016-05-23 | 2016-05-30 | 2016-06-06 | 2016-06-13 | 2016-06-20 | 2016-06-27 | 2016-07-04 | 2016-07-11 | 2016-07-18
2016-02-15 | EBIS |  | Test Mobile App Fixes
| IS |  | Monthly Billing Spec
| Estates |  | Mobile Phone Rollout
| WHO |  | Create demo StartClient Environment
Plan ColdFusion Upgrade
2016-02-22 | EBIS |  |  | Scenario Testing | Scenario Testing
| IS |  |  | Develop Month End Bill +Archivg | Develop Month End Bill +Archivg
2016-02-29 | EBIS |  |  |  | Scenario Testing
| EBIS |  |  |  | Complete PPM Testing on WebCentral
| IS |  |  |  | Develop Month End Bill +Archivg
2016-03-07 | EBIS | IS |  |  |  | Complete ALL testing
| EBIS |  |  |  |  | Month Bill+Achivng User Testing | Month Bill+Achivng User Testing
| IS | EBIS |  |  |  | Month Bill+Archive Rework | Month Bill+Archive Rework
2016-03-14 | [6 empty] | Month Bill+Achivng User Testing
Month Bill+Archive Rework

## FULL Tasks Plan not started
Project: | EST080 | Project Manager: |  |  |  | Anne Mathison | [5 empty] | Business Lead: |  |  |  | Colin Pritchard | [9 empty] | Project:
Date | Team | Liason | 2016-02-15 | 2016-02-22 | 2016-02-29 | 2016-03-07 | 2016-03-14 | 2016-03-21 | 2016-03-28 | 2016-04-04 | 2016-04-11 | 2016-04-18 | 2016-04-25 | 2016-05-02 | 2016-05-09 | 2016-05-16 | 2016-05-23 | 2016-05-30 | 2016-06-06 | 2016-06-13 | 2016-06-20 | 2016-06-27 | 2016-07-04 | 2016-07-11 | 2016-07-18 | Date
2016-02-15 | EBIS |  | Test Mobile App Fixes | Test Mobile App Fixes | Test Mobile App Fixes | Team Sign off | [19 empty] | 2016-02-15
| IS Dev |  | Monthly Billing Spec
| MASS |  | Windows client changes - not heard update yet
| IS Dev |  | EBIS Online Changes - waiting to hear from Mass
| EBIS |  | Review WebCentral Reporting - to be arranged 22-Feb or 29 Feb
| Estates |  | Mobile Phone Rollout Completed
| Estates, AS |  | Create demo StartClient Environment - to be arranged
| IS |  | Plan ColdFusion Upgrade EST091
2016-02-22 | EBIS |  |  | Scenario Testing | [21 empty] | 2016-02-22
| IS |  |  | Develop Month End Bill +Archivg | Spec will be revied this week by Pauline , missing PAT testing
| MASS |  |  | Windows client changes - still being discussed
| IS Dev |  |  | EBIS Online Changes - still being discussed
| Colin, Chris |  |  | Review WebCentral Reporting EST092 | Review WebCentral Reporting EST092
| Colin |  |  | Confim operational requirements EST092 Planning | Confim operational requirements EST092 Planning
| Estates, AS |  |  | Create demo StartClient Environment
| IS - Chris |  |  | Plan ColdFusion Upgrade EST091
2016-02-29 | EBIS |  |  |  | Scenario Testing Plan to start Wed | [20 empty] | 2016-02-29
| IS |  |  |  | Develop Month End Bill +Archivg - Anne discuss with Mike Wed
| EBIS |  |  |  | Test dual fault reporting
| Estates, AS |  |  |  | Create demo SmartClient Environment in progress
| IS - Chris | Colin |  |  | Confim operational requirements EST092 Planning
| IS - Chris |  |  |  | Update Dev EST091
2016-03-07 | EBIS |  |  |  |  | Complete WebCentral Testing | [19 empty] | 2016-03-07
| EBIS |  |  |  |  | Month Bill+Achivng User Testing
| IS | EBIS |  |  |  | Month Bill+Archive Rework
| Estates, AS |  |  |  |  | Create demo StartClient Environment
| IS - Chris |  |  |  |  | Confim operational requirements EST092 Planning
| IS - Chris |  |  |  |  | Update Dev EST091
2016-03-14 | EBIS | [5 empty] | Month Bill+Achivng User Testing | [18 empty] | 2016-03-14
| EBIS | IS |  |  |  |  | Month Bill+Archive Rework
| EBIS | [5 empty] | Complete parallel HD testing | work order sequencing is a prerequesite in test before this can take place
| EBIS | IS |  |  |  |  | Complete ALL system testing
| Estates, AS | chk |  |  |  |  | Arrange demo of SmartClient to Space Planners
Determine Strategy to create mobile friendly floor
| IS | [5 empty] | Update Dev EST091
2016-03-21 | Trades/EBIS | [6 empty] | 1.User consultation/awareness
| CP,MM | [6 empty] | Business Fault Reporters Consultation
| Space Planners | [6 empty] | create mobile floor plans
IS Apps test Dev EST091
2016-03-28 | EBIS | [7 empty] | Complete Month-End Recharging and Archiving
| Trades/EBIS | [7 empty] | 2 User consultation/awareness
| CP,MM | [7 empty] | Business Fault Reporters Consultation
| Space Planners | [7 empty] | create mobile floor plans
| IS | [7 empty] | Update Test EST091 + SO
2016-04-04 | Trades/EBIS | [8 empty] | 3. User consultation/awareness | [15 empty] | 2016-04-04
| CP,MM | [8 empty] | Business Fault Reporters System Consultation
| Project Team | [8 empty] | Prepare User Guide
| Space Planners | [8 empty] | create mobile floor plans
| EBIS | [8 empty] | Test TEST EST091 +SO
2016-04-11 | CP,MM | [9 empty] | Business Fault Reporters System Consultation | [14 empty] | 2016-04-11
| Project Team | [9 empty] | Prepare User Guide
| EBIS | [9 empty] | Complete LIVE configuration
| Estates Space Planners | confirm? | [8 empty] | create mobile floor plans
| IS | [9 empty] | update LIVE EST091
| EBIS | [9 empty] | test LIVE EST091 + SO
2016-04-18 | CP,MM | [10 empty] | Business Fault Reporters System Consultation | [13 empty] | 2016-04-18
| Project Team | [10 empty] | Prepare User Guide
| EBIS | [10 empty] | Complete LIVE configuration
2016-04-25 | CP,MM | [11 empty] | Business Fault Reporters System Consultation | [12 empty] | 2016-04-25
Prepare User Guide
| EBIS | [11 empty] | Complete LIVE configuration
2016-05-02 | CP,MM | [12 empty] | Business Fault Reporters System Consultation | [11 empty] | 2016-05-02
| Project Team | [12 empty] | Review and complete User Guide
| EBIS | [12 empty] | Complete LIVE configuration
2016-05-09 | EBIS | [13 empty] | complete zone related user configuration | [10 empty] | 2016-05-09
2016-05-16 | [15 empty] | complete user training - zone champions (1) | [9 empty] | 2016-05-16
2016-05-23 | [16 empty] | complete user training (1) | [8 empty] | 2016-05-23
Deploy Mobile apps to Trades phones
Go Live Zone (1)
2016-05-30 | [17 empty] | Post Go Live Zone (1) | [7 empty] | 2016-05-30
Project: | EST080 | Project Manager: |  |  |  | Anne Mathison | [5 empty] | Business Lead: |  |  |  | Colin Pritchard | [9 empty] | Project:
Date | Team | Liason | 2016-02-15 | 2016-02-22 | 2016-02-29 | 2016-03-07 | 2016-03-14 | 2016-03-21 | 2016-03-28 | 2016-04-04 | 2016-04-11 | 2016-04-18 | 2016-04-25 | 2016-05-02 | 2016-05-09 | 2016-05-16 | 2016-05-23 | 2016-05-30 | 2016-06-06 | 2016-06-13 | 2016-06-20 | 2016-06-27 | 2016-07-04 | 2016-07-11 | 2016-07-18
Formulas:
Review WebCentral Reporting EST092 = [Review WebCentral Reporting EST092]+7
Month Bill+Archive Rework = [Review WebCentral Reporting EST092]+7
Month Bill+Archive Rework = [Month Bill+Archive Rework]+7