Accommodation Services Programme

2015-16 Mid-Year Review

Attendees: David Slyth (DS), Andy Stewart (AS)
As a follow up to the programme meeting on 11th November, the following actions relating to the projects in the 2015-16 programme still to commence;

- AP56-056: Upgrade KX TEST Infrastructure

  - This project is to be withdrawn from the programme

  - As a result, the programme budget will be reduced by 60 days relating to

    - 50 days associated with the project budget

    - 10 days from the Sponsor Funded balance row

  - This has formally been submitted to the WIS meeting on 4th December

- AP56-057: Booking Agent Interface

  - This project is still scheduled to be completed within the 2015-16 programme

  - The start date is now scheduled for February 2016

  - No change to the estimated 10 days project budget

- AP56-058:  Migration of Kx to Cloud Environment

  - This project is to be withdrawn from the programme

  - As a result, the programme budget will be reduced by 120 days relating to

    - 100 days associated with the project budget

    - 20 days from the Sponsor Funded balance row

- AP56-059: Delivered Catering

  - This project is still anticipated to be commenced in 2015-16.  However, as it is still unclear whether this work will be supplied by a bespoke development by Kinetics or outsourced from another vendor

  - As a result, the programme budget will be reduced by 25 days

  - 5 days should be set aside to undertake the project set-up and planning with the remaining 25 days carried forward into 2016-17

  - The associated contingency budget of 5 days will be retained

  - The start date is now scheduled for June  2016

- Summary of Programme Budget Changes

| Approved Budget: 246 days |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Original Budget |  |  | Revised Budget |  |  | Days Withdrawn |  |  |
|  | Project | Contingency | Total | Project | Contingency | Total | Project | Contingency | Difference |
| ACSP01 Planning for Projects | 6 | 0 | 6 | 6 | 0 | 6 | 0 | 0 | 0 |
| ACS033 Student Application Enhanced Feed | 8 | 0 | 8 | 8 | 0 | 8 | 0 | 0 | 0 |
| ACS034 Cashless Catering | 2 | 0 | 2 | 6 | 0 | 6 | 0 | 0 | +4 |
| AP56-056: Upgrade KX TEST Infrastructure | 50 | 10 | 60 | 0 | 0 | 0 | 50 | 10 | -60 |
| AP56-057: Booking Agent Interface | 10 | 5 | 15 | 10 | 5 | 15 | 0 | 0 | 0 |
| AP56-058: Migration of Kx to Cloud Environment | 100 | 20 | 120 | 0 | 0 | 0 | 100 | 20 | -120 |
| AP56-059: Delivered Catering External | 30 | 5 | 35 | 5 | 5 | 10 | 25 | 0 | -25 |
| Total | 206 | 40 | 246 | 35 | 10 | 41 | 175 | 30 | 45 days |