New College Library

Funk Donation Projects Update

November 2015

The Funk Projects

Creating a treasure house of New College Library Special Collections through:

- Access

- Conservation

- Security

Financial update

| Financial Plan 2015-16 | Estimated spend 2015-16 | Actual spend so far 2015-16 |
| --- | --- | --- |
| Cataloguing Projects - Cataloguer salaries | £67,000 | £15,803 |
| New College Special Collections Curator | £22,500 | £5625? |
| Preservation & Conservation Projects - Book moving - Boxing / hoovering / conservation staff costs | £4300 | £365 £1917 |
| Preservation materials for Archive Collections | £3000 | £0 |
| Funk Projects Exhibition and Publication | £8000 | £0 |
| Other - VAT charge still outstanding for Andrew Walls Library (CSWC) Project Work | £ 2434 | £0 |
| TOTAL | £ 107,234 | £23,710 |

Funk Balance at November 2015 (post-final instalment) =  £119,000 [awaiting confirmation from Development Office 9/11/15]

Funding post-Funk

- Dr Funk delivered his final cheque in Sept 2015. The School are approaching him about a further donation - but not for New College Library

- CLR approached the School about including objectives for New College Library Special Collections in the Divinity School Plan, generating an interesting discussion. They have agreed that “The School of Divinity will continue to identify sources of funding for materials purchases and cataloguing work from New College [i.e. the Church] and any other available funds.” They’re also suggesting approaching Dr Funk to fund “the creation of a public exhibition space in the sanctuary corridor” of New College Library.

Projects 2015-2016

Cataloguing Projects.

- 35,789 items handled via Funk Projects and 28,711 Funk records added/amended so far

- Hymnology (Patrick Murray and Oreste de Tomasso) 4079

- MH – (Paul Nicholas) 228

- TR – (Janice Gailani) 947

- Uncatalogued Pamphlets – Janice has now completed work on this with over 3,000 pamphlets which had not been identified in the original Pamphlets cataloguing assessment now catalogued.

Archives Projects

- Our New College Curator, Kirsty Stewart, has been continuing to work on developing the archive collections at New College and the Centre for World Christianity.  We’ve also been approached by Prof. Fergusson about a new collection, the Anne Hepburn Papers which relate to the ‘Motherhood of God’ debate in the Church of Scotland.

Preservation and Conservation Projects.

- Peter Scott will be ending his preservation work for the Funk Projects in December 2015.He has completed a substantial amount of work cleaning, tying, boxing and rearranging catalogued collections, most recently the Dumfries Presbytery Library. Graeme Darling continues to support us with Special Collections bookmoving work.

- Kirsty Stewart requested a budget for purchasing boxes and preservation materials for the collections she is working with. As the £6020 originally forecast to be spent on preservation work will now be reduced, we agreed that up to £3000 could be available for preservation materials.

- It should be noted that there was remedial conservation work identified in the conservation survey of the Dumfries Presbytery Library, carried out in 2013, which has not yet been actioned. It was hoped that there would be funds remaining at the end of the Funk Projects to achieve this.

- There are additional funds to the Funk Funds available in the New College Library Book Sale Funds (£6500) which could be used for conservation work and preservation materials. A vertical standing exhibition case to be placed in the New College Library Hall might also be a possibility.

Exhibitions

- The exhibition to mark the conclusion of the Funk Projects has been booked for Aug-Oct 2016 in the CRC Display Wall. The exhibition proposal was approved by the University Collections Exhibition Panel in Oct 2015, with a working title of ‘Given in Good Faith’. The exhibition will highlight unique and rare items catalogued as part of the Funk Projects, in the context of the narrative of the founding and development of New College Library.

Volunteer Projects

- Donations Register. Our two volunteers have continued to work on transcribing this register of the original donations to New College Library in 1843-1853. These records contain provenance for many of New College Library’s unique and valuable items and will inform the exhibition work above.

Christine Love-Rodgers

November 2015