COM007 – IDM Migration and Grouper Upgrade

Meeting to be held

Wednesday, 26th March 2014

2.00 – 3.00

Venue Room 160, Old College

AGENDA

Item

- Welcome and Introduction.

- Project Overview (KS)

- Project Progress(KS)

- Project Change Log (KS)

- Project Plan (KS)

- Project Risk update (KS)

- Service Management Update (AC)

- Agree date and format of next meeting (All)

In attendance

Stuart McFarlane, Karen Osterburg, Dave Berry, Susan McLaren, Adam Wadee, Richard Good, Alex Carter, Karen Stirling

Apologies

Graeme Wood

PROJECT OVERVIEW

COM007 IDM Migration and Grouper Upgrade project includes the following phases: - Phase 1: Migrate Push services IDM(includes ARCHIVE, Central Auth, DIALUP, EASE, FORUMS, LAPLAN, MyEd, PEBBLEPD, Unix timeshare, VPN, WIKI, WIRELESS) - Phase 2: Migrate Inbound Services (Golden Copy Connectors) - Phase 2.5: Email provisioning to IDM. - Phase 3: Pull services IDM (this includes UNIDESK, Timetabling, OLL, LEARN, HR, Exchange, e-Time, ECA, e-Recruitment , Active Directory) - Phase 4 Grouper: The version of Grouper will be upgraded after assessment of the benefits the available versions will bring.

PROJECT PROGRESS

- OVERALL PROJECT STATUS

- AMBER: This is due to delays with Phase 1 delivery, and risk that project may go over budget.

- Achievements in Last Period - Peer testing completed and JIRA fixing for Phase 1 in progress on IDM and UI builds. - Deployment to TEST for the SOA Composite and VRS has completed - TEST and Live VM for the new IDM UI has been built and available for deployment - Phase 1 UAT testing is in progress, 95% complete - Archiving script has been written and will be run to reduce the number of outstanding notifications. - Phase 2 System Design Specification signed off following design review - Re-estimation complete for Phase 2 - Re-estimation for phase 2.5 underway Issues - Deployment for Phase 1 took longer than planned. - Serious performance problems encountered on Test. These took substantial time and effort to track down. - TEST VM not available for deployments of the IDM UI. - TAD for Phase 1 delays in sign off encountered - UAT has taken longer than planned as the issues that have arisen are more complex and the UAT testers have other commitments on their time. Next Steps - Complete sign off of TAD as all other details have been completed for Phase 1. - Determine cause of delay in Phase 1 deployment to avoid delays on the LIVE deployment. - Complete build of TEST and LIVE VMs for IDM UI. - Re-plan milestones for ongoing and subsequent phases based on Lessons Learned from Phase 1. - Complete review and sign off of BRD for 3. - Phase 2 Inbound – review and agree plan - Phase 2.5 – re-estimation of effort underway Milestones as of 7th March: - 3rd March - Complete LIVE VM build now complete - 19th March - Complete UAT - 20th March Load Testing starts - 31th March ASOR, Acceptance Sign Off. - w/c 7th April Deploy to LIVE – date to be rearranged due to other activity within SACS impacting dates - 17th April DSOR/Closure – to be reviewed in alignment with new deployment date

PROJECT CHANGE LOG

Change Approved on 6th March for 20 additional IS days provided for the “IDM Dashboard build”, as IS APPs had a developer who had no other planned work. This was added to the programme and portfolio budget and so does not affect the budget available for core work.

PROJECT PHASE STATUS

| Phase 1: Migrate Push services IDM | AMBER – delay in deployment of UI and extended UAT timescales |
| --- | --- |
| Phase 2: Migrate Inbound Services | AMBER - timeline change / milestone review required due to Phase 1 |
| Phase 2.5: Email provisioning to IDM | AMBER - timeline change / milestone review required due to Phase 1 |
| Phase 3: Pull services IDM | AMBER - timeline change / milestone review required due to Phase 1 |
| Phase 4: Grouper | AMBER - timeline change / milestone review required due to Phase 1 |

IS App Staff Resource

Summary as at 28/02/2014 - 247 days effort delivered by IS Apps as at 28th February 2014. - Total Budget for Project now 530 days effort following additional approved scope increase of dashboard of 20 days. - Current Forecast: 567 days - A re-estimation for Phase 2 has been completed amounting to 114 days - Budget for Email provisioning is set at 30days. The original estimate was for design & build only; this needs to be re-estimated. - Proposal for re-estimation of Phase 3 & 4 required as the timeline for the project will extend further into financial year 14/15 and 84 days set aside will have to be reviewed. Also require to include additional project management days to cover handover to new PM.

Approved Budget Position

| 2012/13 | 2013/14 | 2014/15 |
| --- | --- | --- |
| 56 | 390 | 84 |
| Total Budget 530 days |  |  |

PROJECT MILESTONES

| Date |  |  |  | Milestone | Status |
| --- | --- | --- | --- | --- | --- |
| 28-Jun-13 |  |  |  | Brief Sign Off | Complete |
| 31-Jul-13 |  |  |  | Phase 1 Push - Initiate BRD sign off | Complete |
| 18-Sep-13 |  |  |  | Phase 1 Push - Design sign Off | Complete |
| 07-Nov-13 |  |  |  | Phase 1 Design TAD | Complete |
| 28-Nov-13 |  |  |  | Phase 2 Inbound - Initiate BRD | Complete |
| 17-Dec-13 |  |  |  | Phase 1 Push - Build sign Off | Complete |
| 12-Mar-14 |  |  |  | Phase 2 Inbound - Design Sign Off | Complete |
| 31-Mar-14 |  |  |  | Phase 1 Push - ASOR | In progress |
| 11-Apr-14 |  |  |  | Phase 1 Push - Deploy | Change date |
| 17-Apr-14 |  |  |  | Phase 1 Push - DSOR/Closure | Change date |
| 27-May-14 |  |  |  | Phase 2 Inbound - Build Sign off | Proposed |
| 10-Jul-14 |  |  |  | Phase 2 Inbound - ASOR | Proposed |
| 17-Jul-14 |  |  |  | Phase 2 Inbound - Deploy | Proposed |
| 24-Jul-14 |  |  |  | Phase 2 Inbound – DSOR/Closure | Proposed |

The following milestones required to be re-planned and agreed:

Milestone

Phase 2.5 Email Provisioning build Review

Phase 2.5 Email Provisioning ASOR

Phase 2.5 Email Provisioning Closure

Phase 3 Pull - Initiate

Phase 3 Pull - Design Sign Off

Phase 3 Pull - Build Sign Off

Phase 3 Pull - ASOR

Phase 3 Pull - Deploy

Phase 3 Pull - DSOR/Closure

Phase 4 Grouper - Design Sign Off

Phase 4 Grouper - Build Sign Off

Phase 4 Grouper - Initiate

Phase 4 Grouper - ASOR

Phase 4 Grouper - Deploy

Phase 4 Grouper - DSOR/Closure

COM007 - Project Closure

PROJECT RISKS

Commentary

New risk has been raised regarding Email provisioning work

| Ref | Title | Impact | Probability | Status | Risk Owner | RAG |
| --- | --- | --- | --- | --- | --- | --- |
|  | Availability of DEV Tech staff to Contribute to the project | High | Medium | Open | Iain Fiddes | Amber |
|  | Availability of Development team staff to Contribute to the project | High | Low | Open | Richard Good | Amber |
|  | Grouper Version currently unsupported by development Community | Medium | Medium | Open | Chris McKay | Amber |
|  | Service Management Availability | Medium | Low | Open | Chris McKay | Amber |
|  | Developing on New Technology | High | Medium | Open | Karen Stirling | Amber |
|  | Business Area Availability and System Usage Cycles | Medium | High | Open | Karen Stirling | Amber |
|  | Limited SOA experience within DEV Tech | Medium | Medium | Open | Iain Fiddes | Green |
| New | Email Provisioning Work | Medium | High | Open | Karen Stirling | Green |

Notes and Guidance:

Probability - we use the categories LOW, MEDIUM, HIGH and CRITICAL. This assessment is based on the collective judgement of the Project Manager and Risk Owner and is informed by risk assessment on other similar projects. There is no corresponding % based probability.

| Probability Category | Numeric Score |
| --- | --- |
| LOW | 1 |
| MEDIUM | 2 |
| HIGH | 3 |
| CRITICAL | 4 |

For probability we will also often consider when the risk might occur as some risks may be predicted to be further away in time than others. For example in a procurement project there may be a risk that more suppliers will bid than has been planned for resulting in additional work and cost for the project. This risk will only occur or not when the bids are in - depending on the stage of the project this may be soon or some time away. This is sometimes called the risk proximity. Proximity can be used to ensure that attention is focused on the most immediate risks

Impact - is the effect or result of the risk actually happening and takes into account the effects on: time/schedule, cost, quality, scope, benefits and people. For impact we use the categories LOW, MEDIUM, HIGH and CRITICAL. This assessment is based on the collective judgement of the Project Manager and Risk Owner and is informed by risk assessment on other similar projects. There is no corresponding cash value or other measurement of impact.

| Impact Category | Numeric Score |
| --- | --- |
| LOW | 1 |
| MEDIUM | 2 |
| HIGH | 3 |
| CRITICAL | 4 |

Risk Response/Mitigation - suitable responses are aimed at reducing the impact, probability or both. Typical responses break into broadly four types:

- Remove/Prevent/Avoid - terminate the risk by putting in place counter measures which stop the risk from occurring or prevent it from having any impact e.g. by doing thing differently, using different resources etc.

- Reduce - take action to control the risk by reducing the likelihood or limiting the impact to acceptable levels

- Transfer - transfer the risk to a third party e.g. via a specialist insurance arrangement with a third party. This response is relatively rare in practice.

- Retain/Accept/Monitor -  tolerate the risk, e.g. because nothing cost effective can be done to mitigate, or the probability and impact are already at an acceptable level

| Risk Profile RAG Status | Recommended Minimum Actions |
| --- | --- |
| GREEN | Project Manager and risk owner continue to monitor |
| AMBER | Project Manager and risk owner to review and escalate if required |
| RED | Project Manager and risk owner to review, recommend further mitigation actions and escalate to Project Sponsor and Project Board for further review and approval |