## Header
Three Point Estimate
Instructions:
| Project Code/Name: | STU236
| Project Manager | Sally Hayward
| Estimate Date | 2014-04-10
| Project Stage | Execute
| Estimate Reference | v2.0
Notes and Assumptions
Estmate Contributors
| Role |  | Name | Signature
Include all contributors here. Remember to include key IS and business stakeholders such as Unix FM, Architecture, Finance and Procurement where appropriate. Without this information the estimate cannot be approved!
Enter the a,m, and b values for each Task into columns C,D and E. The E and SD values for each task will be calculated and displayed in columns F and G. A task estimate with at least 95% confidence and the required task booking value is calculated and displayed in columns H and J.
Based on the individual task estimates the E value and SD for the project will be calculated and displayed as will the overall work estimate for the project with at least 95% confidence levels.

## Three Point Estimates
Methodology Stage or Activity | Task | Team(s), Role(s) or Individual(s) Responsible for Execution of Task | Best Case Estimate a | Most Likely Estimate m | Worst Case Estimate b | E Value | SD Value | Task Estimate 95% Confidence | SD**2
| Project Management | Project Manager | 14 | 15 | 16 | 15 | 0.4 | 15.8 | 0.2
| Quality Assurance | IS Apps | 1.5 | 2 | 2.5 | 2 | 0.2 | 2.4 | 0.1
Planning | Planning | Project Services | 1.5 | 2 | 2.5 | 2 | 0.2 | 2.4 | 0.1
Business Analysis | Business Analysis for Radium | Business Analyst | 5.5 | 6 | 6.5 | 6 | 0.2 | 6.4 | 0.1
[6 empty] | 0 | 0 | 0
Remaining tasks for Phase 1 SQL/ Coldfusion Upgrade
| Support Testing on DEV | Development Services - Development Technolog, Production Management Application Management | 2 | 3 | 4 | 3 | 0.4 | 3.8
| Migrate to LIVE | Development Services - Development Technolog, Production Management Application Management | 1 | 2 | 2.5 | 2 | 0.3 | 2.6
| Deploy to LIVE and support any issues | Development Services - Development Technolog, Production Management Application Management | 1 | 2 | 2.5 | 2 | 0.3 | 2.6
Waiting List Enhancements (changes for 2 lists), DSA Process Improvements | Work for KELSO system that has been signed off in the Business Requirements Document
Systems Design | Systems Design | Development Services | 1 | 1.5 | 2 | 1.5 | 0.2 | 1.9 | 0.1
| Waiting List modicifcations | Development Services | 27 | 30 | 33 | 30 | 1 | 32 | 1
| Peer Testing | Development Services | 1.5 | 2 | 2.5 | 2 | 0.2 | 2.4 | 0.1
| System Documentation | Production Management - Applications Management | 1 | 1 | 1 | 1 | 0 | 1 | 0
| Implementation Plan | Development Services - Development and Configuration Team | 1 | 1.5 | 2 | 1.5 | 0.2 | 1.9 | 0.1
Radium Enhancements
Business Analysis
Systems Design | Systems Design | Development Services | 3 | 3 | 3 | 3 | 0 | 3 | 0
| Radium Enhancements | Development Services | 10 | 12 | 14 | 12 | 0.7 | 13.4 | 0.5
| Peer Testing | Development Services | 1 | 1 | 1 | 1 | 0 | 1 | 0
| System Documentation | Production Management - Applications Management | 1 | 1 | 1 | 1 | 0 | 1 | 0
| Implementation Plan | Development Services - Development and Configuration Team | 1 | 1.5 | 2 | 1.5 | 0.2 | 1.9 | 0.1
0
| Totals |  |  |  |  | 87 |  | 96
| E (Project Work) |  | 87
| SD (Project Work) |  | 2
| Project Estimate > 95% Confidence |  | 96

## Estimate By Team (IS Apps)
IS Apps Section | Team | Estimate (Days) | SD**2
Project Services | Project Services |  | #REF!
Development Services | Development Team
| Configuration Team |  | #REF!
| Development Technology |  | #REF!
Production Management | Applications Management
| Technology Management |  | #REF!
Service Management | Delivery and Integration | None Required
| Multimedia | None Required | #REF!
Directors Office | Directors Office | None Required
| Total Days | 0