## SItes
KEY |  | cPanel
Plesk
AWS
Scheduled for closure
IS Apps Hosting
Transition out of LTS portfolio (owner to take responsibility)
Service Name | Owner | Migration status (Migrated / In Progress / Ready / Not migrated / Not To Be Migrated | OS | DB | Target WebServer | Target WebServer | SSL
archive.euanmacdonaldcentre.com | WGI IC (IS LTW) | Not To Be Migrated
bmto.ed.ac.uk | LTS | Not To Be Migrated | n/a
bookings.mvm.ed.ac.uk | LTS | ? | n/a |  |  |  | Valid until 21/05/2015
breastcancer.mvm.ed.ac.uk | WGI IC (IS LTW) | Not Migrated | Windows | MSSQL | Plesk | Plesk
carmms.mvm.ed.ac.uk | WGI IC (IS LTW) | Not Migrated | Windows | MSSQL | Plesk | Plesk
cdll.mvm.ed.ac.uk | LTS | Not To Be Migrated | n/a
chronic-migraine.co.uk | WGI IC (IS LTW) | Not Migrated | Windows | MSSQL | Plesk | Plesk
climate.ed.ac.uk | WGI IC (IS LTW) | Not Migrated | Linux | MySQL | winwebat2.is.ed.ac.uk
clinicalaudit.mvm.ed.ac.uk | WGI IC (IS LTW) | Not Migrated | Windows | MSSQL | Plesk | Plesk
clinicaleducation-old.mvm.ed.ac.uk | LTS | Not to be Migrated
clinicaleducation.mvm.ed.ac.uk | DLAM AD (IS LTW) | Migrated | Linux | MySQL | cPanel | cPanel | Valid until 12/03/2016
com-mand.info | DLAM AD (IS LTW) | Not Migrated | Windows | MySQL | collmed.is.ed.ac.uk | sql-db-collmed | Valid until 24/06/2016
demo.essq.ed.ac.uk | DLAM AD (IS LTW) | Migrated | Linux | n/a | cPanel | cPanel
dentistry.mvm.ed.ac.uk | DLAM AD (IS LTW) | Not To Be Migrated
diabetestraining.org ¦ diabetestraining.org ¦ diabetescompetencies.org ¦ diabetescompetencies.org ¦ diabetesframe.org | WGI IC (IS LTW) | Not Migrated | Windows | MSSQL | Plesk | Plesk
eemec.med.ed.ac.uk | DLAM AD (IS LTW) | Not Migrated | Windows | MSSQL/MySQL | eemec.is.ed.ac.uk | sql-db-eemec | Valid until 04/11/2016
eemed.mvm.ed.ac.uk | LTS | Not To Be Migrated
eepop.mvm.ed.ac.uk | LTS | Not To Be Migrated
eevec.vet.ed.ac.uk | DLAM AD (IS LTW) | Not Migrated | Windows | MSSQL | collmed.is.ed.ac.uk | sql-db-collmed | Valid until 13/05/2017
egrad.mvm.ed.ac.uk | LTS | Not To Be Migrated
emsec.mvm.ed.ac.uk | LTS | Not To Be Migrated
eros.mvm.ed.ac.uk | DLAM AD (IS LTW) | Not Migrated | Windows | MSSQL | collmed.is.ed.ac.uk | sql-db-collmed | Valid until 18/04/2016
escript.law.ed.ac.uk | DLAM AD (IS LTW) | Not Migrated | Windows | MSSQL | winwebat2.is.ed.ac.uk | sql-db-winweb | Valid until 23/05/2015
ewriting.org.uk ¦ ewriting.org.uk | EDE (IS LTW) | Not Migrated | Windows | MSSQL | Plesk | Plesk
exam.mvm.ed.ac.uk | DLAM AD (IS LTW) | Not Migrated | Windows | MSSQL | cmvmexam.is.ed.ac.uk | sql-db-cmvmexam | Valid until 24/11/2017
gpst.mvm.ed.ac.uk | DLAM AD (IS LTW) | Migrated | Linux | MySQL | cPanel | cPanel | Valid until 03/09/2016
gracescore.co.uk | WGI IC (IS LTW) | Migrated | Linux | MySQL | cPanel | cPanel
heartelearning.org | WGI IC (IS LTW) | Not Migrated | Linux | MySQL | cPanel | cPanel
hme.mvm.ed.ac.uk | DLAM AD (IS LTW) | Not Migrated | Windows | MSSQL | Plesk | Plesk
iconzafrica.com ¦ iconzafrica.org ¦ iconzafrica.com ¦ iconzafrica.net ¦ iconzafrica.net | WGI IC (IS LTW) | Not Migrated | Windows | MSSQL | Plesk | Plesk
infectioncontrol.mvm.ed.ac.uk | WGI IC (IS LTW) | Not Migrated | Windows | MSSQL | Plesk | Plesk
labyrinth.mvm.ed.ac.uk | DLAM AD (IS LTW) | Not Migrated | Windows | MSSQL | winwebat2.is.ed.ac.uk | sql-db-winweb | Valid until 13/04/2018
learning-analysis.info | DLAM AD (IS LTW) | Not to be Migrated | Linux |  | AWS | AWS | Valid until 07/12/2015
learning.essq.ed.ac.uk | DLAM AD (IS LTW) | Not Migrated | Windows | MySQL | winwebat2.is.ed.ac.uk | sql-db-winweb | Valid until 22/04/2018
learning.gensurg.ed.ac.uk | DLAM AD (IS LTW) | Not Migrated | Windows | MySQL | winwebat2.is.ed.ac.uk | sql-db-winweb
learning.orthosurg.ed.ac.uk | DLAM AD (IS LTW) | Not Migrated | Windows | MySQL | winwebat2.is.ed.ac.uk | sql-db-winweb
learning.urosurg.ed.ac.uk | DLAM AD (IS LTW) | Not Migrated | Windows | MySQL | winwebat2.is.ed.ac.uk | sql-db-winweb
learning.vascular.ed.ac.uk | DLAM AD (IS LTW) | Not Migrated | Windows | MySQL | winwebat2.is.ed.ac.uk | sql-db-winweb
lodopp.net | WGI IC (IS LTW) | Not Migrated | Windows | MSSQL | Plesk | Plesk
lts-archive.mvm.ed.ac.uk | WGI IC (IS LTW) | Not Migrated | Windows | MSSQL | Plesk | Plesk
malawi.mvm.ed.ac.uk | EDE (IS LTW) | Not Migrated | Windows | MSSQL | Plesk | Plesk
medine2.com | WGI IC (IS LTW) | Not Migrated | Windows | MSSQL | Plesk | Plesk
medine2.info ¦ medine2.info ¦ medine2.org ¦ medine2.org ¦ medine2.com | WGI IC (IS LTW) | Not Migrated | Windows | MSSQL | Plesk | Plesk
ooer.labyrinth.mvm.ed.ac.uk | DLAM AD (IS LTW) | Not Migrated | Windows | MSSQL | winwebat2.is.ed.ac.uk | sql-db-winweb
opthalmology.mvm.ed.ac.uk | DLAM AD (IS LTW) | Not Migrated | Windows | MySQL | winwebat2.is.ed.ac.uk | sql-db-winweb | Valid until 22/04/2018
oralhealth.mvm.ed.ac.uk | LTS | Not To Be Migrated | n/a
orthotherapy.mvm.ed.ac.uk | LTS | Not To Be Migrated | n/a
oscaplus.net | DLAM AD (IS LTW) | Not Migrated | Windows | MySQL | collmed.is.ed.ac.uk | sql-db-collmed | Valid until 11/03/2016
pathcal.ac.uk | DLAM AD (IS LTW) | Not Migrated | Windows | MSSQL | collmed.is.ed.ac.uk | sql-db-collmed | Valid until 04/03/2017
pdc-demo.dentistry.ed.ac.uk | DLAM AD (IS LTW) | Migrated | Linux | n/a | cPanel | cPanel
pdc.dentistry.ed.ac.uk | DLAM AD (IS LTW) | Not Migrated | Windows | MySQL | winwebat2.is.ed.ac.uk | sql-db-winweb | Valid until 11/10/2015
pft.mvm.ed.ac.uk - to be archived READ ONLY post sept 14 | DLAM AD (IS LTW) | Not Migrated | Windows | MSSQL | collmed.is.ed.ac.uk | sql-db-collmed | Valid until 15/02/2016
portfolio.mvm.ed.ac.uk | DLAM AD (IS LTW) | Not Migrated | Windows | MSSQL | winwebat2.is.ed.ac.uk | sql-db-winweb | Valid until 23/04/2017
psapilot.net | DLAM AD (IS LTW) | Not to be Migrated | Linux |  | AWS | AWS
recal.mvm.ed.ac.uk | WGI IC (IS LTW) | Not Migrated | Windows | MSSQL | Plesk | Plesk
scottishdoctor.org | LTS | Not To Be Migrated | n/a
sefce.net | DLAM AD (IS LTW) | Migrated | Linux | MySQL | cPanel | cPanel | Valid until 08/08/2016
socletrial.org | WGI IC (IS LTW) | Not Migrated | Windows | MSSQL | Plesk | Plesk
strokeadvancingmodules.org | WGI IC (IS LTW) | Not Migrated | Windows | MSSQL | Plesk | Plesk
strokecorecompetencies.org | WGI IC (IS LTW) | Not Migrated | Windows | MSSQL | Plesk | Plesk
stroketraining.org | WGI IC (IS LTW) | Not Migrated | Windows | MSSQL | Plesk | Plesk
tuning-medicine.com | WGI IC (IS LTW) | Not Migrated | Windows | MSSQL | Plesk | Plesk
tutorialbooking.com | DLAM AD (IS LTW) | Not Migrated | Linux | MySQL | cPanel | cPanel | Valid until 20/09/2015
virtualpharmacologylab.com | WGI IC (IS LTW) | Not Migrated | Windows | MSSQL | Plesk | Plesk
www.clive.ed.ac.uk | LTS | Not To Be Migrated | n/a
[8 empty] | #REF! | #REF!