COM007 – IDM Migration and Grouper Upgrade

Meeting to be held

Tuesday, 20 May 2014

12.30pm – 1.30pm

Room 4.09, Dalhousie Land

AGENDA

Item

- Welcome and Introduction.

Paper A

- Project Overview (KS)

- Project Status(KS)

- Project  Review by Stage(KS)

- Project Risk update (KS)

Paper B

- Project Options

- Agree date and format of next meeting (All)

In attendance

Stuart McFarlane, Karen Osterburg, Dave Berry, Susan McLaren, Adam Wadee, Richard Good, Alex Carter, Karen Stirling, Graeme Wood

Apologies

# PROJECT OVERVIEW

COM007 IDM Migration and Grouper Upgrade project currently includes the following phases: - Phase 1: Migrate Push services - Phase 2: Migrate Inbound Services (Golden Copy Connectors) - Phase 2.5: Email provisioning to IDM. - Phase 3: Pull services - Phase 4 Grouper: The version of Grouper will be upgraded after assessment of the benefits the available versions will bring.

# PROJECT STATUS

The project has completed Phase 1 and is about to enter the testing for Phase 2.

The budget situation is poor and adjustments to the scope of the project will be necessary in order to complete the compliance work required to update the IDM to supported platforms (ORACLE SOA 11G, Grouper v2.1.x). Please see Paper B for a discussion of these options and recommendations from the project team.

## PROJECT BUDGET (IS-Apps staff resource)

### APPROVED BUDGET POSITION

| 2012/13 | 2013/14 | 2014/15 |
| --- | --- | --- |
| 56 | 453 | 84 |
| Total Budget 593 days |  |  |

### PROJECT CHANGE LOG

Agreement given by Programme Manager and Project Sponsor to increase budget by 63 days from ISG Portfolio to cover overspend on project

### IS APP STAFF RESOURCE

Summary as at 30/04/2014 - 444 days effort delivered by IS Apps as at 28th April 2014. - Total Budget for Project 593 days effort See Paper B for discussion of options.

# DETAILED REPORT BY PHASE

## Phase 1 – Notifications to services

Status: GREEN

Stage: Delivered

### Milestones

| Date | Milestone | Status |
| --- | --- | --- |
| 16-Apr-14 | Phase 1 Push - ASOR | Complete |
| 22-Apr-14 | Phase 1 Push - Deploy | Complete |
| 08-May-14 | Phase 1 Push - DSOR/Closure | In plan |

### Issues

- Phase 1 Load testing delayed due to resource constraints / conflict with COM008 taking priority

- Phase 1 Push Services – Pebblepad issue with https connection investigated, resolved and deployed to live, DSOR sign off delayed by 1 week

### Deliverables

- Move to a fully supported platform (SOA 11G)

- Management of IDM Services in new User Interface & decommission of buggy Services User Interface from VRS

- Significantly improved tracking of notifications for auditing and reporting

- Granular notification settings so services receive significantly less irrelevant information

- Improved data accuracy for card numbers, UIDs

## Phase 2 – Changes from Gold Masters

Status: GREEN

Stage: IN PROGRESS, Peer Testing underway

### Milestones

| Date | Milestone | Status |
| --- | --- | --- |
| 20-May-14 | Phase 2 Inbound - Build Sign off | In plan |
| 19-Jun-14 | Phase 2 Inbound - ASOR | In plan |
| 26-Jun-14 | Phase 2 Inbound - Deploy | In plan |
| 03-Jul-14 | Phase 2 Inbound – DSOR/Closure | In plan |

### Issues

- Phase 2 re-estimated and plan reviewed, milestones agreed

- Phase 2 SCA Composite Build and Unit Testing complete

### Deliverables

- Move to a fully supported platform (SOA 11G)

- Student/Applicant Sync tool

- Reactivate UUNs for returning staff/visitors

- Org Unit Level 4 (PoS)/6(Course) for students

## Phase 2.5 – Email Service in IDM

Status: RED – re-estimation has increased the estimate for completion of this work.

Stage: Planning. Proposed to be withdrawn from scope

### Deliverables

- Staffmail/Office 365 service determined by IDM and Staffmail accounts only provisioned if needed

- Gold master data for mail service held in IDM and available to other systems

## Phase 3 – Pull Services

Status: AMBER - new milestones to be agreed if approval to complete remaining requirements in one Phase for Pull Services IDM / Grouper

Stage: Planning. Proposed to be combined with Phase 4

### Deliverables

- Move to a fully supported platform (SOA 11G)

- Store per-service ageing status (A, E, S) in database for pull services/support checking.

## Phase 4 – Grouper Upgrade

Status: AMBER - new milestones to be agreed if approval to complete remaining requirements in one Phase for Pull Services IDM / Grouper

Stage: Planning. Proposed to be combined with Phase 3

### Deliverables & Benefits

- Move to a supported version (Grouper 2.1.x)

- Improvements to LDAP provisioning

- Various bug fixes and new features

- Roll-out of ad-hoc groups by use of group types

- Performance improvements for IDM processes

- Integration with Active Directory

## PROJECT RISKS

Commentary

| Ref | Title | Impact | Probability | Status | Risk Owner | RAG |
| --- | --- | --- | --- | --- | --- | --- |
|  | Availability of DEV Tech staff to Contribute to the project | High | Medium | Open | Iain Fiddes | Amber |
|  | Availability of Development team staff to Contribute to the project | High | Low | Open | Richard Good | Amber |
|  | Grouper Version currently unsupported by development Community | Medium | Medium | Open | Chris McKay | Amber |
|  | Service Management Availability | Medium | Low | Open | Chris McKay | Amber |
|  | Developing on New Technology | High | Medium | Open | Karen Stirling | Amber |
|  | Business Area Availability and System Usage Cycles | Medium | High | Open | Karen Stirling | Amber |
|  | Limited SOA experience within DEV Tech | Medium | Medium | Open | Iain Fiddes | Green |
|  | Email Provisioning Work | Medium | High | Open | Karen Stirling | Green |