## Three Point Estimate - No SSP
Methodology Stage or Activity | Task | Team(s), Role(s) or Individual(s) Responsible for Execution of Task | Best Case Estimate a | Most Likely Estimate m | Worst Case Estimate b | E Value | SD Value | Task Estimate 95% Confidence | SD**2 | Stage totals
Management | Project Management | Project Services | 25 | 30 | 35 | 30 | 1.7 | 33.4 | 2.9
| Programme Management | Project Services | 0.5 | 2 | 3 | 2 | 0.5 | 3 | 0.3
| Portfolio Management | Project Services | 0.2 | 1.5 | 2 | 1.4 | 0.3 | 2 | 0.1 | 38.4
Initiation | Initiation | Project Services | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0.5 | 0 | 0.5
|  | Software Dev - SSP |  |  |  | 0 | 0 | 0 | 0 | 0
Planning | Planning | Project Services | 1 | 2 | 2 | 1.9 | 0.2 | 2.3 | 0.1
| Planning | Software Dev - SSP | 0.2 | 0.3 | 0.4 | 0.3 | 0.1 | 0.5 | 0.1
| Planning | Production Management | 0.2 | 0.3 | 0.4 | 0.3 | 0.1 | 0.5 | 0.1
| Planning Review | All | 0.1 | 0.2 | 0.3 | 0.2 | 0.1 | 0.4 | 0.1 | 3.7
Business / System Analysis - SMID | Business Analysis | Project Services | 0.2 | 0.3 | 0.5 | 0.4 | 0.1 | 0.6 | 0.1
| Business Analysis support | Software Dev - SSP |  |  |  | 0 | 0 | 0 | 0
| Analysis Review | All | 0.2 | 0.3 | 0.5 | 0.4 | 0.1 | 0.6 | 0.1 | 1.2
Systems Design - SIMD | Planning | Project Services |  |  |  | 0 | 0 | 0 | 0
| Familiarisation | Software Dev - SSP |  |  |  | 0 | 0 | 0 | 0
| Design Review | All |  |  |  | 0 | 0 | 0 | 0 | 0
Build - SIMD | Build & Dev testing | Software Dev - SSP |  |  |  | 0 | 0 | 0 | 0
| Dev Tech Support | Dev Tech |  |  |  | 0 | 0 | 0 | 0
| Build Review | All |  |  |  | 0 | 0 | 0 | 0 | 0
Build - SharePoint | 2018 Site Development | Software Dev - SSP |  |  |  | 0 | 0 | 0 | 0
Integration | Integration | Software Dev - SSP |  |  |  | 0 | 0 | 0 | 0
| Integration Review | All | 0.2 | 0.5 | 0.7 | 0.5 | 0.1 | 0.7 | 0.1 | 0.7
Acceptance | Acceptance Testing | Project Team |  |  |  | 0 | 0 | 0 | 0
| Address UAT feedback | Software Dev - SSP |  |  |  | 0 | 0 | 0 | 0
| Deployment Checklist | Apps Mgt | 0.1 | 0.2 | 0.2 | 0.2 | 0.1 | 0.4 | 0.1
| Acceptance Review | All | 0.1 | 0.3 | 0.5 | 0.3 | 0.1 | 0.5 | 0.1 | 0.9
Deployment | Deployment | Dev Tech | 0.1 | 0.2 | 0.3 | 0.2 | 0.1 | 0.4 | 0.1
| Deployment | Apps Mgt | 0.1 | 0.1 | 0.2 | 0.2 | 0.1 | 0.4 | 0.1
| Deployment Review | All | 0.1 | 0.2 | 0.3 | 0.2 | 0.1 | 0.4 | 0.1 | 1.2
Handover | Handover - 2019 Process | Apps Mgt | 0.2 | 1 | 1.5 | 1 | 0.3 | 1.6
|  | Software Dev - SSP |  |  |  | 0 | 0 | 0
Closure | Closure | Project Services | 0.2 | 0.5 | 0.7 | 0.5 | 0.1 | 0.7 | 0.1
| Closure Review | All | 0.2 | 0.5 | 0.5 | 0.5 | 0.1 | 0.7 | 0.1 | 1.4
| Totals |  |  |  |  | 41 |  | 50
| E (Project Work) |  | 41
| SD (Project Work) |  | 3
| Project Estimate > 95% Confidence |  | 50

## Header
Three Point Estimate
Instructions:
| Project Code/Name: | USG006 Clearing 2017
| Project Manager | Emma McNab
| Estimate Date | 2017-06-01
| Project Stage | Planning
| Estimate Reference | USG006.01
Notes and Assumptions
Please record any notes and assumptions on which the estimate is based.
1
Estmate Contributors
| Role |  | Name | Signature
Include all contributors here. Remember to include key IS and business stakeholders such as Unix FM, Architecture, Finance and Procurement where appropriate. Without this information the estimate cannot be approved!
| Project manager |  | Emma McNab
| SSP Lead |  | Defeng Ma
Designer / Developer
Production Support lead
Production Support team leader
| Production Support lead & team leader |  | Heather Larnach
Enter the a,m, and b values for each Task into columns C,D and E. The E and SD values for each task will be calculated and displayed in columns F and G. A task estimate with at least 95% confidence and the required task booking value is calculated and displayed in columns H and J.
Based on the individual task estimates the E value and SD for the project will be calculated and displayed as will the overall work estimate for the project with at least 95% confidence levels.

## Three Point Estimate - Inc SSP
Methodology Stage or Activity | Task | Team(s), Role(s) or Individual(s) Responsible for Execution of Task | Best Case Estimate a | Most Likely Estimate m | Worst Case Estimate b | E Value | SD Value | Task Estimate 95% Confidence | SD**2 | Stage totals
Management | Project Management | Project Services | 25 | 30 | 35 | 30 | 1.7 | 33.4 | 2.9
| Programme Management | Project Services | 0.5 | 2 | 3 | 2 | 0.5 | 3 | 0.3
| Portfolio Management | Project Services | 0.2 | 1.5 | 2 | 1.4 | 0.3 | 2 | 0.1 | 38.4
Initiation | Initiation | Project Services | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0.5 | 0 | 0.5
|  | Software Dev - SSP | 0.1 | 0.2 | 0.3 | 0.2 | 0.1 | 0.4 | 0.1 | 0.4
Planning | Planning | Project Services | 1 | 2 | 2 | 1.9 | 0.2 | 2.3 | 0.1
| Planning | Software Dev - SSP | 0.2 | 0.3 | 0.4 | 0.3 | 0.1 | 0.5 | 0.1
| Planning | Production Management | 0.2 | 0.3 | 0.4 | 0.3 | 0.1 | 0.5 | 0.1
| Planning Review | All | 0.1 | 0.2 | 0.3 | 0.2 | 0.1 | 0.4 | 0.1 | 3.7
Business / System Analysis - SMID | Business Analysis | Project Services | 0.2 | 0.3 | 0.5 | 0.4 | 0.1 | 0.6 | 0.1
| Business Analysis support | Software Dev - SSP | 0.2 | 0.3 | 0.5 | 0.4 | 0.1 | 0.6 | 0.1
| Analysis Review | All | 0.2 | 0.3 | 0.5 | 0.4 | 0.1 | 0.6 | 0.1 | 1.8
Systems Design - SIMD | Planning | Project Services |  |  |  | 0 | 0 | 0 | 0
| Familiarisation | Software Dev - SSP |  |  |  | 0 | 0 | 0 | 0
| Design Review | All |  |  |  | 0 | 0 | 0 | 0 | 0
Build - SIMD | Build & Dev testing | Software Dev - SSP |  |  |  | 0 | 0 | 0 | 0
| Dev Tech Support | Dev Tech |  |  |  | 0 | 0 | 0 | 0
| Build Review | All |  |  |  | 0 | 0 | 0 | 0 | 0
Build - SharePoint | 2018 Site Development | Software Dev - SSP | 2 | 5 | 8 | 5 | 1 | 7 | 1
Integration | Integration | Software Dev - SSP | 2 | 3 | 4 | 3 | 0.4 | 3.8 | 0.2
| Integration Review | All | 0.2 | 0.5 | 0.7 | 0.5 | 0.1 | 0.7 | 0.1 | 4.5
Acceptance | Acceptance Testing | Project Team |  |  |  | 0 | 0 | 0 | 0
| Address UAT feedback | Software Dev - SSP | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0.5 | 0
| Deployment Checklist | Apps Mgt | 0.1 | 0.2 | 0.2 | 0.2 | 0.1 | 0.4 | 0.1
| Acceptance Review | All | 0.1 | 0.3 | 0.5 | 0.3 | 0.1 | 0.5 | 0.1 | 1.4
Deployment | Deployment | Dev Tech | 0.1 | 0.2 | 0.3 | 0.2 | 0.1 | 0.4 | 0.1
| Deployment | Apps Mgt | 0.1 | 0.1 | 0.2 | 0.2 | 0.1 | 0.4 | 0.1
| Deployment Review | All | 0.1 | 0.2 | 0.3 | 0.2 | 0.1 | 0.4 | 0.1 | 1.2
Handover | Handover - 2019 Process | Apps Mgt | 0.2 | 1 | 1.5 | 1 | 0.3 | 1.6
|  | Software Dev - SSP | 0.2 | 1 | 1.5 | 1 | 0.3 | 1.6
Closure | Closure | Project Services | 0.2 | 0.5 | 0.7 | 0.5 | 0.1 | 0.7 | 0.1
| Closure Review | All | 0.2 | 0.5 | 0.5 | 0.5 | 0.1 | 0.7 | 0.1 | 1.4
| Totals |  |  |  |  | 52 |  | 64
| E (Project Work) |  | 52
| SD (Project Work) |  | 3
| Project Estimate > 95% Confidence |  | 64

## Estimate By Team (IS Apps)
IS Apps Section | Team | Estimate (Days) | SD**2
Project Services | Project Services | 42.5 | #VALUE!
Development Services | Software Dev - SSP | 14.4
| Dev Tech | 0.4 | #VALUE!
Production Management | Apps Mgt | 2.4
| Technology Management | 0 | #VALUE!
| Service Management | 0
IS Applications | All | 3.3
| Total Days | 63