## Activity Creation
Step | Process | Description | Application | Sub-application | Unexpected Behaviour | Improvements from previous release
Creating Activity Template
1 | Open Module Editor | Open Module Editor using 'Show' button | ECP | Module Editor | as expected | no
2 | Expand selected Module | Click on the small plus sign in Module to expand | ECP | Module Editor | as expected | slight delay when first expanded but very fast after this
3 | Create Activity Template | Highlight Module and click 'Create Activity Template' | ECP | Module Editor | as expected | seemed faster
4 | Check that sort filter is working | Click into Activity Type field and check that *s are at the top of the list | ECP | Module Editor | as expected | they now actually start with the *s as first options
5 | Apply changes | Click 'Apply' and wait until 'OK' button becomes highlighted again | ECP | Module Editor | as expected | bit of a delay about 3 seconds
6 | Writeback | Click 'Writeback' | ECP | Dashboard | as expected | none
Generating Activity from Template
1 | Open Template Editor | Open Template Editor using 'Show' button | ECP | Template Editor | as expected | as per pervious version
2 | Expand selected Template | Click on the small plus sign in Template to expand | ECP | Template Editor | as expected | slight delay when first expanded but very fast after this
3 | Generate Activity | Click on 'Cog' symbol to generate an Activity | ECP | Template Editor | as expected | slight delay before it shows an activity has been created but in one test did not show till I had clicked apply
4 | Apply changes | Click 'Apply' and wait until 'OK' button becomes highlighted again | ECP | Template Editor | as expected | seemed faster
5 | Writeback | Click 'Writeback' | ECP | Dashboard | as expected | the same
Working with Activity in TT
1 | Check that auto filter row is available | Check whether 'Auto filter row' is automatically active in Views menu | Timetabler | N/A | had to add so expected behaviour | had to add the auto filter row
2 | Select Modules from Views menu | Select Modules from Views menu | Timetabler | N/A | as expected
3 | Highlight Activity | Select Module and highlight desired Activity | Timetabler | N/A | as expected
4 | Open Resources tab | Move from Combined Timetable to Resources | Timetabler | N/A | as expected
5 | Extend Day/Time field | Click on small plus sign in Day/Time field | Timetabler | N/A | as expected | opened fatser
6 | Extend Location field | Click on small plus sign in Location field | Timetabler | N/A | as expected | took about 1.5s to open
7 | Change Requirement | Click 'Change Requirement' | Timetabler | N/A | as expected
8 | Search for a Location | Click 'Search' to identify available Locations based on selections | Timetabler | N/A | as expected
9 | Select and Accept Location | Highlight preferred Location and click 'Accept' | Timetabler | N/A | as expected
10 | Writeback | Click 'Writeback' | Timetabler | N/A | as expected | very fast but only having to writeback one change
11 | Refresh | Click 'Refresh' | Timetabler | N/A | as expected

## Student Allocation
Step | Process | Description | Application | Sub-application | Unexpected Behaviour | Improvements from previous release
Allocate students within a Template
1 | Open Template Editor | Open Template Editor using 'Show' button | ECP | Template Editor | as expected
2 | Select Template and open Template Allocator | Click on 'Template Allocator' in order to open allocation window | ECP | Template Editor | slight delay when first opening, but after this worked fine
3 | Allocate by Name | Allocate students using 'Allocate by Name' allocation option | ECP | Template Allocator | as expected
4 | Apply changes | Click 'Apply' and wait until 'OK' button becomes highlighted again | ECP | Template Allocator | took about 30s before OK appeared
5 | Writeback | Click 'Writeback' | ECP | Dashboard | as expected | very fast but probably due to only one change being made.
6 | Allocate Evenly | Allocate students using 'Allocate Evenly' allocation option | ECP | Template Allocator | seemd to freeze for about 20s then came back with the allocation | still having the same issues when allocating large numbers | for a class greater than 250 took over 5 mins to allocate had to close down before allocation completed
7 | Allocate Randomly | Allocate students using 'Allocate Randomly' allocation option | ECP | Template Allocator | as expected
Unallocate students within a Template
1 | Highlight all students in order to Unallocate | Highlight all student in order to Unallocate | ECP | Template Allocator | as expected
2 | Unallocate | Click 'Unallocate' | ECP | Template Allocator | as expected
3 | Apply changes | Click 'Apply' and wait until 'OK' button becomes highlighted again | ECP | Template Allocator | as expected
4 | Writeback | Click 'Writeback' | ECP | Dashboard | as expected
Amending student allocations within a Template
1 | Move a student from one Activity to another within one Template | Double click in 'allocation box' to allocate student to desired Activity | ECP | Template Allocator | faster | now only need to click once so speeds up the process
2 | Apply change | Click 'Apply' and wait until 'OK' button becomes highlighted again | ECP | Template Allocator | as expected
3 | Writeback | Click 'Writeback' | ECP | Dashboard | as expected
4 | Refresh | Click 'Refresh' | ECP | Dashboard | as expected

## Gatekeeping
Step | Process | Description | Application | Sub-application | Unexpected Behaviour | Improvements from previous release
Confirming WRB requests
1 | Select Activity Filter from Views menu | Select Activity Filter from Views menu | Timetabler | N/A | as expected
2 | Set filter by desired parameters | Select 'Activity Types: WRB Active' and 'Status: Unscheduled' | Timetabler | N/A | as expected
3 | Apply filter | Click 'Apply Filter' | Timetabler | N/A | as expected | returned results a bit quicker
4 | Filter Activities to a specific Department | Use 'filter funnel' to select a Department | Timetabler | N/A | as expected
5 | Schedule Activity | Highlight Activity, right click on blue diamond and 'Schedule Here' | Timetabler | N/A | as expected
6 | Writeback | Click 'Writeback' | Timetabler | N/A | as expected
Unscheduling WRB cancelled requests
1 | Select Activity Filter from Views menu | Select Activity Filter from Views menu | Timetabler | N/A | as expected
2 | Set filter by desired parameters | Select 'Activity Types: WRB Cancelled' and 'Status: Scheduled' | Timetabler | N/A | as expected
3 | Apply filter | Click 'Apply Filter' | Timetabler | N/A | as expected
4 | Filter Activities to a specific Department | Use 'filter funnel' to select a Department | Timetabler | N/A | n/a as no results returned
5 | Unschedule Activity | Highligh Activity, right click and select 'Unschedule' | Timetabler | N/A | n/a as no results returned
6 | Writeback | Click 'Writeback' | Timetabler | N/A | n/a as no results returned
Confirming Pending Requests In
1 | View all Pending Requests In | Click 'Pending Requests (in)' to view outstanding requests | Timetabler | N/A | as expected
2 | Highlight request to be allocated | Highlight request to be allocated | Timetabler | N/A | as expected
3 | Grant request | Click 'Actions', 'Requests', 'Grant Request' | Timetabler | N/A | as expected
4 | Writeback | Click 'Writeback' | Timetabler | N/A | as expected | seemed quicker
Creating an Activity from a Resource
1 | Select Locations from Views menu | Select Locations from Views menu | Timetabler | N/A | as expected
2 | Highlight desired Location | Click on Location in Views pane and wait for associated Activities to appear in Activities pane | Timetabler | N/A | as expected | loaded quite quickly
3 | Select week or weeks | Select week or weeks | Timetabler | N/A | as expected
4 | Open Activity Editor | Open Activity Editor by clicking 'Edit, Create Activity' | Timetabler | N/A | took about 15s after I clicked okay before I could click save
5 | Save Activity in Local copy | Save Activity by clicking 'Save' | Timetabler | N/A | as expected
6 | Schedule Activity | Highlight Activity, right click on blue diamond and 'Schedule Here' | Timetabler | N/A | as expected
7 | Writeback | Click 'Writeback' | Timetabler | N/A | as expected
8 | Refresh | Click 'Refresh' | Timetabler | N/A | as expected

## Extras
Step | Process | Description | Application | Sub-application | Unexpected Behaviour | Improvements from previous release
Creating a jointly taught Activity
1 | Select Modules from the Views menu | Select Modules from the Views menu | Timetabler | N/A | as expected
2 | Highlight Activity and select Jointly Taught Activity | Highlight Activity and click 'Actions, Jointly Taught Activity' | Timetabler | N/A | as expected
3 | Select Candidate(s) for sharing | Select the Module of the Activity to be joined with Primary Activity in the Candidates for sharing box, and move it up to be joined | Timetabler | N/A | as expected
4 | Save jointly taught Activity | Click 'OK' in order to save/ create jointly taught Activity | Timetabler | N/A | as expected
5 | Open Resources tab | Move from Combined Timetable to Resources | Timetabler | N/A | as expected
6 | Extend Day/Time field | Click on small plus sign in Day/Time field | Timetabler | N/A | as expected
7 | Extend Location field | Click on small plus sign in Location field | Timetabler | N/A | as expected
8 | Change Requirement | Click 'Change Requirement' | Timetabler | N/A | as expected
9 | Search for a Location | Click 'Search' to identify available Locations based on selections | Timetabler | N/A | as expected
10 | Select and Accept Location | Highlight preferred Location and click 'Accept' | Timetabler | N/A | as expected
11 | Writeback | Click 'Writeback' | Timetabler | N/A | as expected
Creating a variant
1 | Select Modules from views menu | Select Modules from views menu | Timetabler | N/A | as expected
2 | Highlight activity to be varianted | Highlight activity to be varianted | Timetabler | N/A | as expected
3 | Enter Variant Mode | Click on 'Variant Mode' symbol | Timetabler | N/A | as expected
4 | Selct week(s) to be Varianted | Select the week to variant and enter the Resources tab | Timetabler | N/A | as expected
5 | Move selected week to a new Location | Use the 'Search' button to identify an alternative Location and click 'Accept' | Timetabler | N/A | as expected
6 | Writeback | Click 'Writeback' | Timetabler | N/A | as expected
7 | Refresh | Click 'Refresh' | Timetabler | N/A | as expected

## What's new in 3.11
Application | Enhancement | Detail | Test | Outcome | Comments
ECP/RDM/TT | Timed refresh reminder | Version 3.11 adds options to automatically carry out a refresh and to specify a countdown interval. The user can control the refresh interval and countdown timer warning to fit with current working practices. | 1. Set refresh interval 2. Change refresh/countdown interval 3. Check saving of latest settings | 1. Passed 2. Passed 3. Passed
ECP/RDM | Filter builder | Version 3.11 adds the ability to build a filter based on the relationships an object has to other objects; for example, a user could filter locations based on the suitabilities with which they are associated | 1. Filter by 'suitability' 2. Filter by 'Tag' 3. Filter by multiples (Suitability/Tags) | 1. Passed 2. Passed 3. Failed
TT | Trusted write | When Enterprise applications interact with the Syllabus Plus image they can now use a trusted write to make changes such that a reschedule of the activity is not required. The application itself will carry out any corollary changes that are required, avoiding the need to arbitrarily reschedule the activity with the attendant risk of failure to reschedule. | 1. Make amendment to 'problem' activity 2. Check successful reschedule 3. Check impact on problem count
ECP/TT | Improved synchronisation | The Enterprise applications obtain their data from a local database that must be synchronised with changes made in the Syllabus Plus image. Some changes have been made in version 3.11 to improve the efficiency of synchronisation by refining the granularity of change notification supplied by the image. Notably, when there is a change to the problem count, the image now conveys the detail of which problems were changed so that only the relevant records in the local database need to be updated.
ECP/RDM/TT | What-if modelling | In version 3.11, Enterprise Timetabler has a “Snapshot” option that allows the user to choose a name and folder location for the saving of an image. Such images are automatically registered for use with COM as part of the saving process and can be accessed by running Enterprise applications from the Start menu rather than via the Portal. A newly added permission in AM controls whether or not a user has access to this new feature. | 1. Test saving offline 2. Test local launch from Start menu 3. Test AM user access | 1. n/a 2. n/a 3. n/a | No AM access in Beta environment

## What's new in 3.12
Application | Enhancement | Enhancement Detail | Test Scenario | Fail/Pass | Comments | Enterprise Course Planner and Reference Data Manager
AM |  | A missing space between “from” and “role” in the message “Copy rules and role membership from role "Admin" for all applications” is corrected. |  | PASS | now a space
AM |  | In Scientia Notes: One user reports that creating new users or roles or deleting them sometimes results in the error “Entity too large” Although this has been observed in a remote support session it is not reliably reproducible. | N/A | N/A | This was never an issue at UoE
ECP / RDM |  | It is now possible to filter based on multiple values (for those columns where filtering is enabled). |  | Fail | not allowing mutiple selection
ECP / RDM |  | ‘Duration’ is now available as a column in the Activity editor. |  | PASS | no difference as duration was an option before
ECP / RDM |  | ECP and EDRDM will now display a warning of conflicts caused by refreshing from SDB; i.e. where data received in the refresh overwrites data that has not been written back. |  | PASS | checked based on student double allocation
ECP / RDM |  | Host key and user text fields are now available as optional columns against the student set in the template allocation window. |  | PASS
ECP / RDM |  | Allocation of a student set to an activity now requires a single click rather than a double click to change the state of the checkbox. |  | PASS | just one click needed much faster process
ECP / RDM |  | ECP / RDM now supports the option of cloud based logging. | N/A | N/A | This cannot be tested in the dev environment
ECP / RDM |  | Allocation of student sets to activities that are variant parents no longer creates a duplicate student set to activity relationship. The inadvertent duplication previously prevented the local database from being built successfully when using SQL Express. | Check what happens when split up variants
ECP / RDM |  | Invoking the auto-filter row when working in an expanded list no longer causes an error. | N/A | N/A | This has naver been a problem for UoE users.
ECP / RDM |  | Working in the activity grid that is nested underneath the template in the activity template editor no longer causes an “Object reference not set to an instance of an object” error. | N/A | N/A | This cannot be tested due to lack of reference of data causing errors.
ECP / RDM |  | A memory leak that caused ECP to error with a System.OutOfMemory exception was resolved. | N/A | N/A | This problem canot be recreated
ECP / RDM |  | When the “Show jointly taught” option is selected in the template allocation window, changes made to allocations are not correctly committed. Use the option to view allocations made to JTAs but deselect the option before making changes to allocations. |  | PASS | Description Workaround / Action - need to make sure show jointly taught is not selected
ECP / RDM |  | Attempting to filter the template editor by “Existing Activities” causes the application to freeze if the number of distinct entries in that column is large. Do not filter by “Existing Activities” |  | PASS | confirmed this happens
ECP / RDM |  | ECP intermittently seems to fail when handling a group with a large number of members (module group with 2790 members in the reported case). Further investigation required to reproduce this consistently | N/A | N/A | Do not apply to UoE
Enterprise Datasync |  | Datasync now supports the option of cloud based logging. | N/A | N/A | Cannot be tested in dev environment
Enterprise Datasync |  | Datasync is now tolerant of data where the number of characters in user text 1 exceeds the limit of 2000 characters as a result of additional line feed characters being inserted. Excess characters will be truncated in the local database. |  | FAIL | UT1 limited to 1800 characters without spaces
Enterprise Datasync |  | Starting a second Enterprise application against a standalone image (not launched from the portal) when there is already another application running against it and a a local database has been built no longer offers the user the option to rebuild the database. | N/A | N/A | Do not apply to UoE
Enterprise Datasync | Known restrictions discovered in this release | Description Workaround / Action Allocating a student set to an activity in the Allocation tab of the Activity Template window in Syllabus Plus does not trigger a synchronisation. As a result ECP fails to show the changed allocation. Click on the button at the bottom right of the ECP window to force a synchronisation |  | FAIL | allocated students not showing. No button at bottom right of the ECP window
WRB |  | It is now possible to use WRB integrated with the Enterprise Portal without requiring user credentials; e.g. via single sign-on and associated with a role using a plug-in. | N/A | N/A | Cannot be tested in dev environment. To be investigated further when link to downstream interfaces created.
WRB |  | The portal now provides a logout page with a ReturnUrl parameter so that a user that has been logged in other than via the portal page (e.g. a WRB user) can be successfully logged out without being returned to the portal page. | N/A | N/A | Do not apply to UoE
WRB |  | An attempt to write a thread name to an already named thread causing the exception “System.InvalidOperationException: This property has already been set and cannot be modified” was removed. | N/A | N/A | Do not apply to UoE
ET |  | Activity dates are now available as an option in the column chooser for the activity viewer. The user can choose to show individual dates (a list of all the dates when the activity occurs) or a range of dates (start date - end date), available as separate columns. |  | PASS | There are these two new options for columns
ET |  | The choices offered to the user on exit of an Enterprise application are now simplified in a single window where the user can choose whether or not to commit changes to the application memory, the SDB and the locally saved copy of the data. | N/A | N/A | Data by default saved to SDB
ET |  | The names and descriptions of problems and waivers are now correctly internationalised. | N/A | N/A | Do not apply to UoE
ET |  | Resource lists, such as the list of staff or locations, in the Resource Tab are now only populated in memory if the tab is in a state where the lists are visible. This means that the Resource Tab displays more quickly when the lists are not visible. |  | ???? | resources tab opened quickly.
ET |  | The “Keep resources” check box is now selected by default in the Edit Weeks window so that changes to the week pattern will be made without changing allocated resources. |  | PASS | yes this was auto selected
ET |  | The licence server configuration file now points to the C:\scilicen folder by default as the place where licence files will be stored. | N/A | N/A | Do not apply to UoE
ET |  | Course group membership is now included in the schema of the local database. | N/A | N/A | Do not apply to UoE
ET |  | ET will now display a warning of conflicts caused by refreshing from SDB; i.e. where data received in the refresh overwrites data that has not been written back. |  | PASS | yes but we are not sure how we got this to happen. But with auto refresh this would not matter as changes would be made automatically.
ET |  | Enterprise Timetabler now supports the option of cloud based logging. | N/A | N/A | Cannot be tested in dev environment.
ET |  | The message that is logged when the application is unable to access the local database because it is being rebuilt is now correctly categorised as informational so that it is only added to the log file when the level of logging includes INFO. | N/A | N/A | Do not apply to UoE
ET |  | The error “This channel can no longer be used to send messages” no longer occurs when scheduling many activities. | N/A | N/A | Do not apply to UoE
ET |  | Both the list of activities shown when a programme of study is selected in the views list and the programme of study column in the activity list now use the same definition of programme from the underlying Syllabus Plus image. | N/A | N/A | Do not apply to UoE
ET |  | Using the calendar control to select a data in booking mode now correctly shows all the days of the last week of the timetable as available. | N/A | N/A | Do not apply to UoE
ET |  | It is no longer possible for a user without the “Create Activity” permission to copy an activity or create jointly taught activities (as both of these create new activities). | ask Scott |  | test later
ET |  | Splitting a jointly-taught activity no longer results in student sets becoming detached from the former parent activities. |  |  | test later by setting up a specific test case in live
ET |  | The list of Named Availability Patterns is now populated in the local database as soon as it is built. | N/A | N/A | Do not apply to UoE
ET |  | A synchronisation is now invoked after a forced refresh. |  |  | we made a booking in a room on one machine and did not writeback, while on the other machine we made a conflicting booking and scheduled and did a writeback. With the autorefresh on the other user then sees that another booking has been made before they writeback. Only problem is that you can still writeback your booking resulting in a double booking.
ET |  | The week label is now correctly shown when hovering over the week control in the activity window, availability editor. |  | PASS | nice new feature
ET |  | Creating a variant using click and drag to a new time when the selected activity is itself a variant child in a same time relationship now correctly warns the user that the same time relationship will be broken and allows the new variant to be created |  | FAIL | Created a variant of a jointly taught activity, was able to create a variant but when created it disappeared from the activity template and showed no activites. I then set the day and time to nothing and was able to schedule without a warning.
ET |  | The violation colour key is now correctly available after a restart of ET. |  | FAIL | had to select an activity before the violation key could be selected, but had to do this before
ET |  | ET can now handle cases where more than 2100 resources are available in response to a search in the Resource Tab when using SQL Express to manage the local database. | N/A | N/A | Do not apply to UoE
ET |  | The multi-view timetable no longer errors with an “Object reference not set to an instance of an object” message when the user attempts to drag and drop an activity. | N/A | N/A | Do not apply to UoE
ET |  | A booking activity is now correctly created whether or not a suitability requirement has been specified. |  | PASS | is this a feature that is a help???
ET | Known restrictions discovered in this release | The screen redraw interval (in Tools ¦ Options) allows negative integers even though a negative number makes no sense in this context. Avoid setting the number to a negative integer. Most users will not need to change the value from the default. | N/A | N/A | Do not apply to UoE
Syllabus Plus | functional changes at this release. | Changes have been made to prevent the image from retaining references to deleted objects. In previous versions this could happen when, for example, one user associates an activity with an activity type while another user deletes that activity type and writes back the deletion. |  |  | need to test later
Syllabus Plus | functional changes at this release. | A stackdump file (sometimes generated when Syllabus Plus errors) is now named with the ProgId of the image, the date and the time when it was created, making it easier to distinguish if multiple stackdumps have been generated or are being analysed. |  |  | Stuart Craig to look at
Syllabus Plus | functional changes at this release. | A writing back image can now pass to Enterprise applications details of changes at the SDB that conflict with changes that are pending writeback. This information is shown to the user of the Enterprise application that invokes the writeback and is also available through the COM API to applications using COM to invoke a writeback.
Syllabus Plus | functional changes at this release. | The local image is now brought up-to-date with the SDB before attempting to write back local changes. This avoids scenarios where the local image can retain and write back data that is invalid with respect to SDB. The new writeback function is also accessible through the COM interface. | N/A | N/A | Do not apply to UoE
Syllabus Plus |  | An image running as a service will now successfully auto-save on a timed basis. Note that the appropriate write permissions must be granted for a save to succeed. |  |  | Stuart Craig to look at
Syllabus Plus |  | Selecting a Max Workspan constraint in the constraints profile window (by double-clicking) now correctly opens the Max Workspan window rather than the Resource Break window. | N/A | N/A | Do not apply to UoE
Syllabus Plus |  | Deletion of a Pooled Resource now correctly removes scheduled allocations of that Pooled Resource. |  | N/A
Syllabus Plus |  | Setting the student sets of a module no longer results in an error “No method in generic function ck:student-sets” when there are no activities requiring student sets to be removed as a result of the changes. | ask C-A
Syllabus Plus |  | Some incorrect Dutch translations were corrected. | N/A | N/A | Do not apply to UoE
Syllabus Plus |  | Changing student set allocation against the Activity Template now correctly removes the student set from a jointly taught child activity even when the student set is associated with more than one of the parent activities. | ask C-A
Syllabus Plus |  | Changing the available weeks of an object no longer fails on the first attempt. In previous versions the pattern would appear to be changed but revert to its original state on pressing “Modify” |  | PASS | not sure if this was an issue before when done in S+
Syllabus Plus |  | The SDB no longer allows inserts in the SDO_Activity table for previously deleted activities. In previous versions this could lead to the activities being reinstated. |  |  | may need Stuart Craig to look at this
Syllabus Plus |  | Attempting to download data containing a relationship for a deleted object now stops the download with a message to the user and, on closing the image, generates a stackdump that gives details of the offending data, rather than failing with an error message. | need to do this with a previous task
Syllabus Plus |  | The code that calculates soft constraint scores can return incorrect results when one of the elements making up the total score fails to return a result. In such a case the scores from the previous element were being re-used, leading to an inaccurate total score. | check what soft constraint scores means |  | not a priority
Syllabus Plus |  | Supplementary data stored against waivers is now written in such a way that it cannot be misinterpreted when reading back into a refreshing image. In previous versions the misinterpretation was causing the image to error and refresh to fail. |  |  | not sure how we check this. Is this something IS can look at.
Syllabus Plus | Known restrictions discovered in this release | Description: When upgrading from a version earlier than 3.10 to 3.10 or later, departmental hierarchy information is lost when loading a UPF from the pre-3.10 data. WA: Contact support for instructions on saving and editing the UPF to avoid this. | N/A | N/A | Do not apply to UoE
| Known restrictions discovered in this release | Description: An error was experienced during refresh of a connected image with respect to an activity that appears to be valid at SDB. WA: Currently under investigation. There is no way to reliably reproduce the issue. | N/A | N/A | Do not apply to UoE
| Known restrictions discovered in this release | Description: A resource that is allocated to a scheduled activity but no longer a required resource is retained as allocated even if the resource Is deleted and the data can be written back to SDB in this state. WA: Found during internal testing but never reported from real use. Consider for resolution in 3.14. | N/A | N/A | Do not apply to UoE
| Known restrictions discovered in this release | Description: Selecting the activity delivery tab silently removes student sets from the requirement when the student set is not on the module of the activity. WA: Refrain from using the delivery tab while in the S+ UI. The change is only made if the tab is viewed. Consider for resolution in 3.14 | Scott/Marianne to test