## BI Team estimates
Budget estimate for BI resources (v0.7)
|  | Calculation for steady state, full year (19/20 onward) | [8 empty] | Calculation for 2018/19
| FTE | Role | Assumed Grade | Group | Anticipated Resource | Anticipated term for BI role | Avg. On Cost for Grade (19/20) | Day Rate | Days or Salary Basis | Forecast Cost (19/20) | Start Date for BI role | Proportion of Full Year Forecast | Forecast Cost (18/19) | Adjusted Forecast Cost (18/19) |  | Adjustment Notes
| 0.6 | Programme & project manager / support | 8 | Project Services | Geoff Cropley | up to 07/2019 | 63014 | 350 | Day rate | 38850 | 2019-04-15 | 0.29589 | 11495.3425 | 24595.2 |  | 42 days at full rate (£585.60)
| 0.811 | BI Lead | 8 | Project Services | Danny | up to 07/2021 | 63014 | 350 | Salary | 51104.354 | 2018-08-20 | 0.94795 | 48444.1274 | 48444.1274
| 0.5 | BI/MI Business Lead | 9 | GaSP | Lynda | up to 07/2021 ? | 67402 | 350 | Salary | 33701 | 2018-08-01 | 1 | 33701 | 30892.5833 |  | Official start date 1st Sept so 11 months
| 0.2 | Business Analyst | 8 | GaSP | Kevin Harkin | up to 07/2019 | 63014 | 350 | Salary | 12602.8 | 2019-05-13 | 0.21918 | 2762.2575 | 5524.5151 |  | Starting at 0.4 FTE this year
|  | Business Analyst (1 FTE but no cost) |  | SEP Core Systems | * recruiting | up to 07/2020 |  |  |  | 0 | ? |  | 0 | 0
| 0.5 | Data Architect | 8 | Enterprise Arch. | Wilbert | up to 07/2021 | 63014 | 350 | Salary | 31507 | 2019-02-01 | 0.49589 | 15624.0192 | 15624.0192
|  | ** Data Warehouse / ETL Architect ? |  |  | *Contract /Consultant? |  |  |  |  | 0 |  |  | 0 | 0
| 1 | ETL Developer | 8 | Dev | Rob | up to 07/2021 | 63014 | 350 | Salary | 63014 | 2019-05-27 | 0.18082 | 11394.3123 | 9115.4499 |  | 0.2 FTE assigned for HESA return this year
| 1 | ETL Developer | 8 | Dev | Geir | up to 07/2021 | 63014 | 350 | Salary | 63014 | 2019-05-20 | 0.2 | 12602.8 | 11342.52 |  | Approx 0.2 FTE booked during June
| 0.2 | DBA | 8 | Dev Tech | Gillian | up to 07/2021 | 63014 | 350 | Day rate | 12950 | 2019-05-06 | 0.23836 | 3086.7123 | 3086.7123 |  | (might charge ETL on Days basis in 18/19)
| 1 | Report Writer | 7 | Service Mng't | * recruiting | up to 07/2021 | 50162 | 350 | Salary | 50162 | 2019-07-01 | 0.084932 | 4260.3342 | 4260.3342
| 1 | Service Manager / Management | 7 | Service Mng't | Anne | up to 07/2021 | 50162 | 350 | Salary | 50162 | 2018-08-01 | 1 | 50162 | 44054 |  | Actual salary cost for full role (not agreed)
| 0.5 | Production Support | 7 | Production Mng't | * variable - recruiting | up to 04/2021 ? | 50162 | 350 | Salary | 25081 | 2019-04-15 | 0.29589 | 7421.2274 | 7421.2274 |  | => should be no ASTA against DT projects
| 7.311 | [7 empty] | Total Staff | 432148.154 |  |  | Total Staff | 204360.6888
[9 empty] | Training | 10000 |  |  | Training | 5000
|  | ** Note: Data Warehouse / ETL Architect may be required during initial stages. | [6 empty] | Consultancy | 6000 |  |  | Consultancy |  |  | Known Contingency Items
|  | (This could be covered by the backfill funding, but best to get more Dev resources (inc. another ETL developer for capacity) if possible) | [6 empty] | Travel | 1000 |  |  | Travel | 1000 |  | 5000 | additional Agile Training
[9 empty] | Contingency | 20000 |  |  | Contingency | 10000 |  | 5000
|  | Anticipated terms do not reflect current contract end points for individuals, which may be brought in line now funding is fixed up to 07/2021. | [6 empty] | Total | 469148.154 |  |  | Total | 220360.6888
[9 empty] | Budget Surplus | 851.846 |  |  | Budget Surplus | 14439.3112 | …plus £21,000 from HR Applicants if committed.
Days based Costing
|  | Assumptions, Risks & Caveats: | [7 empty] | Expected available DT Budget (less Portfolio Mng't reduction) |  |  |  |  | £9 extra per day for Grade 8's
|  | Funding is guaranteed over the next two academic years to allow recruitment of 2 Year Fixed Term positions. | [8 empty] | 2018/19 | 2019/20 | 2020/21 |  | £79 extra per day for Grade 7's
Ongoing license costs for new BI Tools, EDW, and Talend will be met by ISC going forward (c. £180k per annum not included in this budget).
[10 empty] | BI Resp. Service | 142000 | 470000 | 470000
|  | Project management methodology will be sufficiently agile for 0.6 FTE to manage and report the programme and projects within. | [7 empty] | Key Strategic Info | 137000 | (combined) | (combined) |  | Budget cut by £50k to £500k
|  | BI team resources will be fully committed to the agreed FTEs, resource contention to be escalated to the Project Sponsor. | [7 empty] | HR Applicants? |  |  |  |  | But commited for next 2 years
[10 empty] | Original Budget | 279000 | 470000 | 470000 |  | (DT Governance Board 13/03/2019)
|  | This is a first iteration of the dedicated team required to deliver the DT funded strategic reporting work. | [12 empty] | Accounting for £30k Portfolio Mng't
|  | Additional sponsor funded projects will require additional resourcing and management, separate from and without impacting the dedicated BI Team. | [7 empty] | Less | 7500 | (adj. to match Finance actuals)
|  | (This may be difficult at present given a lack of suitable skills outside the team, and the need for a holistic design as the data warehouse evolves.) | [7 empty] | Transfer to EDW | 19200 |  |  |  | Other Potential Income
[10 empty] | Transfer to REF | 17500 |  |  |  | HR Applicants Project HRS097
[10 empty] | Available Budget | 234800 |  |  |  | 60 days = £21,000

## BI Income & Expenses
BI / MI Programme - Budget Management as at 31/12/2018
Category | Item | Details | Days | Budget | Additional Notes | Future Years | 2019/20 | 2020/21
Income
ISG Bids | BI Reponsive Service Bid | Originally intended to fund the ongoing costs required to run the new BI tools and associated service. |  | 142000 | Originally bid for £300k, cut to £145k in the DT Portfolio review. Leaving £142 after admin overhead deductions. | Original bid £300k, cut to total of £500k at the 13th March DT board. | £500k | £500k
| Key Strategic Information Bid | Originally intended to fund the work to bring data into the data warehouse. |  | 137000 | Originally bid for £150k, cut to £145k in the DT Portfolio review. Leaving £137 after admin overhead deductions. | Original bid £250k, cut to total of £500k at the 13th March DT board.
HR | e-Recruitment Development Supplement | Transfer of 60 days budget in 18/19 to cover 2 x Universes | 60 | 21000
Total Available Budget |  |  |  | 300000 | Note: Eva's financials list combined finances as £271,499.99?
Expenditure
Programme Mng't
Project
External
Training | IRM Conference (PO: IS18133) | Danny, £1531.20 and £239.70 expenses |  | 1770.9
| HE Data Conference (PO: IS18162) | Danny, £474 and £143.20 expenses |  | 617.2
Transferred funds | EDW Programme top up Oct 2018 |  |  | 7500
| EDW Programme top up Dec 2018 |  |  | 11700
| REF data requirements analysis (RIS008) |  | 50 | 17500
Total Spend |  |  |  | 39088.1
Actual Budget Remaining |  |  |  | 260911.9
Expected Spend
| Key Strategic Reporting (DTI049) | Never got put through officially as a project, due to change in strategic focus to work on HR and Finance.
| HR Applications and e-Recruitment (? - Ken PM) | Project to replace the applications BOBJ Universe with a more fitting data mart and anonymised version. HR can contribute 60 days effort in year 2018/19, awaiting prioritsiation and confirmation that we will undertake the work (within the next year). | 78 | 27300
Expected Budget Remaining |  |  |  | 233611.9
Related Items | BI / MI Lead salary costs | DT is funding half of Lynda's post this year, the other half coming from SEP. Unknown if this is to be met by this budget or the cultural adoption pot. |  | 30000