## Header
Three Point Estimate
Instructions:
| Project Code and Name: | STU265 - G-Cloud replacement of FOI Request planning tool
| Project Manager | Ken Miller
| Estimate Date | 2019-07-19
| Project Stage | Planning
| Estimate Reference | v0.3
Notes and Assumptions
Estimates will cover the evaluation, procurement and implimentation of a replacement FOI Request planning tool for Records Management. With the actual replacement tool not yet identified there is a level of contingency included in the estimates. Once the preferred supplier has ben identified estimates will be revisited to provide a more acurate estimate of times and tasks.
Estmate Contributors
| Role |  | Name | Agreement With Estimate (Y/N or Signature)
| Project Manager |  | Ken Miller
| Head of Production Management |  | Stefan Kaempf
| Development Technology |  | Mark Lang
| Software Development |  | Bill Lee
| Applications Services |  | Suran Perera
| Enterprise Architecture |  | Dave Berry
Enter the a,m, and b values for each Task into columns C,D and E. The E and SD values for each task will be calculated and displayed in columns F and G. A "95% confidence" task estimate is calculated and displayed.
Based on the individual task estimates the E value and SD for the project will be calculated and displayed as will the overall 95% confidence work estimate for the project. (Note however that this estimate despite the "95% confidence" tag remains an estimate and is only as good as the information known about the project scope and the work required. Research suggests that even a good estimate produced as part of a ToR or Brief will be accurate to with +/- 20%. It's important to ensure that the project sponsor understands this and that provision is made to handle any cost overruns.)
Finally record any notes, assumptions or issues affecting the estimate and ensure that the names and agreement of all contributors is recorded.

## Three Point Estimate
Stage | Task | Team(s), Role(s) or Individual(s) Responsible for Execution of Task | Best Case Estimate a | Most Likely Estimate m | Worst Case Estimate b | E Value | SD Value | Task Estimate 95% Confidence | SD**2
| Project Management | Project Manager | 6 | 8 | 10 | 8 | 0.7 | 9.4 | 0.5
| Programme Management | Programme Manager | 2 | 2 | 2 | 2 | 0 | 2
Initiate | Project Initiation | Project Manager | 1 | 2 | 3 | 2 | 0.4 | 2.8
Plan | Prepare Project Brief | Project Manager | 3 | 4 | 5 | 4 | 0.4 | 4.8
|  | Development Technology | 0.5 | 0.5 | 1 | 0.6 | 0.1 | 0.8
|  | Apps Management | 0.5 | 0.5 | 1 | 0.6 | 0.1 | 0.8
|  | Enterprise Architecture | 0.5 | 0.5 | 1 | 0.6 | 0.1 | 0.8
| Phase Stage sign-off | Project Team | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0.5
Product Evaluation | Project Management | Project Manager | 4 | 5 | 6 | 5 | 0.4 | 5.8
| Arrange and support evaluation webex and evaluation exercise | Project Manager | 2 | 2 | 2 | 2 | 0 | 2
| DPIA/EQIA | Project Team | 1 | 2 | 3 | 2 | 0.4 | 2.8
| Technical Evaluation | Development Technology | 2 | 2 | 3 | 2.2 | 0.2 | 2.6
|  | Enterprise Architecture | 1 | 1 | 1 | 1 | 0 | 1
| Phase Stage sign-off | Project Team | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0.5
Design/Build | Project Management | Project Manager | 2 | 3 | 4 | 3 | 0.4 | 3.8
| Technical Architecture Document | Development Technology | 2 | 2.5 | 3 | 2.5 | 0.2 | 2.9
| Technical Evaluation | Development Technology | 2 | 2.5 | 3 | 2.5 | 0.2 | 2.9
| Single Sign on Integration | Development Technology | 2 | 2.5 | 3 | 2.5 | 0.2 | 2.9
| Phase Stage sign-off | Project Team | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0.5
Acceptance | Project Management | Project Manager | 3 | 4 | 5 | 4 | 0.4 | 4.8
| Complete successfully, the UAT as detailed in the Evaluation Criteria | Records Management
| Acceptance Support & Re-work | Development Technology | 1 | 1 | 1 | 1 | 0 | 1
| Phase Stage sign-off | Project Team | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0.5
Implementation | Project Management | Project Manager | 2 | 4 | 4 | 3.7 | 0.4 | 4.5
Co-ordinate solution for live usage
Organise user support mechanism in using the solution
| Implementation and Support | Application Services | 4 | 5 | 6 | 5 | 0.4 | 5.8
| Phase Stage sign-off | Project Team | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0.5
Data Migration | Project Management | Project Manager | 2 | 4 | 4 | 3.7 | 0.4 | 4.5
| Analyse historic data | Business Analyst | 3 | 3 | 3 | 3 | 0 | 3
| Complete data ETL | Software Development | 6 | 8 | 10 | 8 | 0.7 | 9.4
Cold Fussion Decommission | Project Management | Project Manager | 2 | 3 | 4 | 3 | 0.4 | 3.8
| Secure data and decommission environment | Development Technology | 3 | 4 | 5 | 4 | 0.4 | 4.8
|  | Technology Management | 3 | 4 | 5 | 4 | 0.4 | 4.8
Close | Project Management | Project Manager | 2 | 2 | 2 | 2 | 0 | 2 | 0
Complete review and confirm no outstanding issues
Complete project closure report
| Phase Stage sign-off | Project Team | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0.5 | 0
| Totals |  |  |  |  | 85 |  | 100
| E (Project Work) |  | 85
| SD (Project Work) |  | 1
| Project Estimate > 95% Confidence |  | 100

## Estimate By Team (IS Apps)
IS Apps Section | Team | Estimate (Days) | SD**2
Project Services | Project Services | 53.2 | #REF!
Development Services | Development Team | 14.2
| Configuration Team |  | #REF!
| Development Technology | 17.9 | #REF!
Production Management | Applications Management | 0.8
| Technology Management | 6.3 | #REF!
| Enterprise Architecture | 1.8
Service Management | Delivery and Integration | 5.8
| Multimedia |  | #REF!
Directors Office | Directors Office
| Total Days | 100