## Header
Three Point Estimate
Instructions:
| Project Code/Name: | EST126 Archibus Database upgrade
| Project Manager | Chris Konczak
Estimate Date
Project Stage
Estimate Reference
Notes and Assumptions
Please record any notes and assumptions on which the estimate is based.
Estmate Contributors
| Role |  | Name | Signature
Include all contributors here. Remember to include key IS and business stakeholders such as Unix FM, Architecture, Finance and Procurement where appropriate. Without this information the estimate cannot be approved!
Enter the a,m, and b values for each Task into columns C,D and E. The E and SD values for each task will be calculated and displayed in columns F and G. A task estimate with at least 95% confidence and the required task booking value is calculated and displayed in columns H and J.
Based on the individual task estimates the E value and SD for the project will be calculated and displayed as will the overall work estimate for the project with at least 95% confidence levels.

## Three Point Estimates
Methodology Stage or Activity | Task | Team(s), Role(s) or Individual(s) Responsible for Execution of Task | Best Case Estimate a | Most Likely Estimate m | Worst Case Estimate b | E Value | SD Value | Task Estimate 95% Confidence | SD**2
| Project Management | Project Services | 7.375 | 10.25 | 13.5 | 10.4 | 1.1 | 12.6 | 1.3
| Programme management | Project Services | 1 | 1.5 | 2 | 1.5 | 0.2 | 1.9
| Resourcing |  |  |  |  | 0 | 0 | 0
| Directors Office | Directors Office | 1 | 2 | 2.5 | 2 | 0.3 | 2.6
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
Planning | Planning | Development Technology | 0.5 | 1 | 1.5 | 1 | 0.2 | 1.4 | 0.1
|  | Technology Management | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0.5
|  | Applications Management | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0.5
|  | Project Services | 2 | 3 | 4 | 3 | 0.4 | 3.8
| Project Review meetings | Development Technology | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0.5
|  | Technology Management | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0.5 |  | Assume 3 x 1 hour progress meeting during each stage = 3 hours
|  | Applications Management | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0.5 |  | x 3 project team
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
Systems Analysis | [5 empty] | 0 | 0 | 0
| Updating the TAD | Development Technology | 0.5 | 0.5 | 1 | 0.6 | 0.1 | 0.8 | 0.1
[6 empty] | 0 | 0 | 0
Systems Design | Systems Design |  |  |  |  | 0 | 0 | 0 | 0
| TAD review | Technology Management | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0.5
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
Build | Database upgrade from Oracle 11g to 12.2 | Development Technology | 3 | 4 | 5 | 4 | 0.4 | 4.8 | 0.2
| Applications Management support | Applications Management | 1 | 1 | 1 | 1 | 0 | 1 | 0
| Technology management support | Technology Management | 1 | 1 | 1 | 1 | 0 | 1
| Rework | Development Technology | 0.5 | 1 | 2 | 1.1 | 0.3 | 1.7
| Rework | Applications Management | 0.5 | 1 | 2 | 1.1 | 0.3 | 1.7
| Rework | Technology Management | 0.5 | 1 | 2 | 1.1 | 0.3 | 1.7
| Optional for VM route - ITI requests / updates | Development Technology | 0.5 | 1 | 1.5 | 1 | 0.2 | 1.4
[6 empty] | 0 | 0 | 0
Integration | Performance tests before, documented | Development Technology | 1 | 1 | 1 | 1 | 0 | 1
[6 empty] | 0 | 0 | 0
| Database upgrade from Oracle 11g to 12.2 | Development Technology | 3 | 4 | 5 | 4 | 0.4 | 4.8 | 0.2
| support for upgrade to TEST | Technology Management | 1 | 1 | 1 | 1 | 0 | 1
| support for upgrade to TEST | Applications Management | 1 | 1 | 1 | 1 | 0 | 1
| Applications Managemen integration testing | Applications Management | 1 | 1 | 1 | 1 | 0 | 1
| Integration testing rework | Development Technology | 0 | 0.5 | 1 | 0.5 | 0.2 | 0.9
| Integration testing rework | Applications Management | 0 | 0.5 | 1 | 0.5 | 0.2 | 0.9
| Integration testing rework | Technology Management | 0 | 0.5 | 1 | 0.5 | 0.2 | 0.9
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
Acceptance | Documentation updates | Development Technology | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0.5 | 0
| Performance tests after, documented | Development Technology | 1 | 1 | 1 | 1 | 0 | 1
| UAT Rework | Development Technology | 0 | 0.5 | 1 | 0.5 | 0.2 | 0.9
| Implementation plan | Development Technology | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0.5
| Deployment checklist | Applications Management | 0.5 | 1 | 1.5 | 1 | 0.2 | 1.4
|  | Technology Management | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0.5
| Handover | Development Technology | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0.2
|  | Technology Management | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0.2
| Pre-go live tasks or fixes from UAT | Development Technology | 0 | 0.5 | 0.5 | 0.5 | 0.1 | 0.7
|  | Applications Management | 0 | 0.5 | 0.5 | 0.5 | 0.1 | 0.7
|  | Technology Management | 0 | 0.5 | 0.5 | 0.5 | 0.1 | 0.7
[6 empty] | 0 | 0 | 0
Deployment | [5 empty] | 0 | 0 | 0 | 0
| Database upgrade from Oracle 11g to 12.2 | Development Technology | 3 | 4 | 5 | 4 | 0.4 | 4.8
| deployment support | Applications Management | 0.5 | 0.5 | 1 | 0.6 | 0.1 | 0.8
| deployment support | Technology Management | 0.5 | 0.5 | 1 | 0.6 | 0.1 | 0.8
| Rework | Development Technology | 0 | 0.5 | 1 | 0.5 | 0.2 | 0.9
| Decommissioning tasks | Development Technology | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0.5
[6 empty] | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
Closure | Closure Report and tasks | Project Services | 1 | 1.5 | 2 | 1.5 | 0.2 | 1.9 | 0.1
| Closure meeting and tasks | Development technology | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0.2 | 0
|  | Applications Management | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0.2
|  | Technology management | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0.2
| Totals |  |  |  |  | 56 |  | 69
| E (Project Work) |  | 56
| SD (Project Work) |  | 2
| Project Estimate > 95% Confidence |  | 69

## Estimate By Team (IS Apps)
IS Apps Section | Team | Estimate (Days) | SD**2
Project Services | Project Services | 20.2 | #REF!
0
Development Services | Software Development | 0
0
| Configuration Team | 0 | #REF!
0
| Development Technology | 27.5 | #REF!
0
Production Management | Applications Management | 9.7
0
| Technology Management | 8.5 | #REF!
0
Service Management | service management | 0
0
| Multimedia | 0 | #REF!
0
Directors Office | Directors Office | 2.6
| Total Days | 68.5